## Book1
Excluded | # | Group Code | Group Description | Desc | Age | Condition | Qty | Item Amount | Unit | Reported Cost | Unit Cost | Coverage | Sales Tax | RCV | Life | Depreciation Type | Depreciation Amount | Recoverable | ACV | Tax | Replace | Cat | Sel | Owner | Original Vendor | Date | Source Name
FALSE | 1 | MAIN_LEVEL | Main Level | Equipment setup, take down, and monitoring (hourly charge) | 0 | Average | 10 | 725.6 | HR | 0 | 72.56 | Dwelling | 0 | 870.72 | 0 | Percent | 0 | Yes | 870.72 | Yes | No | WTR | EQ | DAVID.SO |  | 2022-01-14
FALSE | 2 | MAIN_LEVEL | Main Level | Dumpster load - Approx. 40 yards, 7-8 tons of debris | 0 | Average | 4 | 5932 | EA | 0 | 1483 | Dwelling | 0 | 7118.4 | 0 | Percent | 0 | Yes | 7118.4 | Yes | No | DMO | DUMP>> | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 3 | DINING_ROOM2 | Dining Room | Demolish/remove - bedroom/room (up to 200 sf) | 0 | Average | 121.67 | 829.79 | SF | 0 | 6.82 | Dwelling | 0 | 995.75 | 0 | Percent | 0 | Yes | 995.75 | Yes | No | DMO | HRBDR | DAVID.SO |  | 2022-01-27
FALSE | 4 | DINING_ROOM2 | Dining Room | Clean with pressure/chemical spray | 0 | Average | 121.67 | 53.53 | SF | 0 | 0.44 | Dwelling | 0 | 64.23 | 0 | Percent | 0 | Yes | 64.23 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 5 | DINING_ROOM2 | Dining Room | Apply plant-based anti-microbial agent to the floor | 0 | Average | 121.67 | 42.58 | SF | 0 | 0.35 | Dwelling | 0 | 51.1 | 0 | Percent | 0 | Yes | 51.1 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 6 | DINING_ROOM2 | Dining Room | Air mover (per 24 hour period) - No monitoring | 0 | Average | 6 | 201 | EA | 0 | 33.5 | Dwelling | 0 | 241.2 | 0 | Percent | 0 | Yes | 241.2 | Yes | No | WTR | DRY | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 7 | KITCHEN2 | Kitchen | Demolish/remove - kitchen/laundry | 0 | Average | 111 | 1581.75 | SF | 0 | 14.25 | Dwelling | 0 | 1898.11 | 0 | Percent | 0 | Yes | 1898.11 | Yes | No | DMO | HRK | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 8 | KITCHEN2 | Kitchen | Clean with pressure/chemical spray | 0 | Average | 111 | 48.84 | SF | 0 | 0.44 | Dwelling | 0 | 58.6 | 0 | Percent | 0 | Yes | 58.6 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 9 | KITCHEN2 | Kitchen | Apply plant-based anti-microbial agent to the floor | 0 | Average | 111 | 38.85 | SF | 0 | 0.35 | Dwelling | 0 | 46.63 | 0 | Percent | 0 | Yes | 46.63 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 10 | KITCHEN2 | Kitchen | Dehumidifier (per 24 hour period) - Large - No monitoring | 0 | Average | 3 | 225 | EA | 0 | 75 | Dwelling | 0 | 270 | 0 | Percent | 0 | Yes | 270 | Yes | No | WTR | DHM> | DAVID.SO |  | 2022-01-27
FALSE | 11 | KITCHEN2 | Kitchen | Air mover (per 24 hour period) - No monitoring | 0 | Average | 6 | 201 | EA | 0 | 33.5 | Dwelling | 0 | 241.2 | 0 | Percent | 0 | Yes | 241.2 | Yes | No | WTR | DRY | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 12 | LIVING_ROOM2 | Living Room | Demolish/remove - bedroom/room (up to 200 sf) | 0 | Average | 162.67 | 1109.41 | SF | 0 | 6.82 | Dwelling | 0 | 1331.29 | 0 | Percent | 0 | Yes | 1331.29 | Yes | No | DMO | HRBDR | DAVID.SO |  | 2022-01-27
FALSE | 13 | LIVING_ROOM2 | Living Room | Clean with pressure/chemical spray | 0 | Average | 162.67 | 71.57 | SF | 0 | 0.44 | Dwelling | 0 | 85.89 | 0 | Percent | 0 | Yes | 85.89 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 14 | LIVING_ROOM2 | Living Room | Apply plant-based anti-microbial agent to the floor | 0 | Average | 162.67 | 56.93 | SF | 0 | 0.35 | Dwelling | 0 | 68.31 | 0 | Percent | 0 | Yes | 68.31 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 15 | LIVING_ROOM2 | Living Room | Air mover (per 24 hour period) - No monitoring | 0 | Average | 6 | 201 | EA | 0 | 33.5 | Dwelling | 0 | 241.2 | 0 | Percent | 0 | Yes | 241.2 | Yes | No | WTR | DRY | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 16 | HALLWAY | Hallway | Demolish/remove - bedroom/room (up to 200 sf) | 0 | Average | 110.5 | 753.61 | SF | 0 | 6.82 | Dwelling | 0 | 904.33 | 0 | Percent | 0 | Yes | 904.33 | Yes | No | DMO | HRBDR | DAVID.SO |  | 2022-01-27
FALSE | 17 | HALLWAY | Hallway | Clean with pressure/chemical spray | 0 | Average | 110.5 | 48.62 | SF | 0 | 0.44 | Dwelling | 0 | 58.34 | 0 | Percent | 0 | Yes | 58.34 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 18 | HALLWAY | Hallway | Apply plant-based anti-microbial agent to the floor | 0 | Average | 110.5 | 38.68 | SF | 0 | 0.35 | Dwelling | 0 | 46.42 | 0 | Percent | 0 | Yes | 46.42 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 19 | BEDROOM_2 | Bedroom 2 | Demolish/remove - bedroom/room (up to 200 sf) | 0 | Average | 117.22 | 799.44 | SF | 0 | 6.82 | Dwelling | 0 | 959.32 | 0 | Percent | 0 | Yes | 959.32 | Yes | No | DMO | HRBDR | DAVID.SO |  | 2022-01-27
FALSE | 20 | BEDROOM_2 | Bedroom 2 | Clean with pressure/chemical spray | 0 | Average | 117.22 | 51.58 | SF | 0 | 0.44 | Dwelling | 0 | 61.9 | 0 | Percent | 0 | Yes | 61.9 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 21 | BEDROOM_2 | Bedroom 2 | Apply plant-based anti-microbial agent to the floor | 0 | Average | 117.22 | 41.03 | SF | 0 | 0.35 | Dwelling | 0 | 49.23 | 0 | Percent | 0 | Yes | 49.23 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 22 | BEDROOM_2 | Bedroom 2 | Air mover (per 24 hour period) - No monitoring | 0 | Average | 3 | 100.5 | EA | 0 | 33.5 | Dwelling | 0 | 120.6 | 0 | Percent | 0 | Yes | 120.6 | Yes | No | WTR | DRY | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 23 | MASTER_BEDRO | Master Bedroom | Demolish/remove - bedroom/room (up to 200 sf) | 0 | Average | 157.5 | 1074.15 | SF | 0 | 6.82 | Dwelling | 0 | 1288.99 | 0 | Percent | 0 | Yes | 1288.99 | Yes | No | DMO | HRBDR | DAVID.SO |  | 2022-01-27
FALSE | 24 | MASTER_BEDRO | Master Bedroom | Clean with pressure/chemical spray | 0 | Average | 157.5 | 69.3 | SF | 0 | 0.44 | Dwelling | 0 | 83.16 | 0 | Percent | 0 | Yes | 83.16 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 25 | MASTER_BEDRO | Master Bedroom | Apply plant-based anti-microbial agent to the floor | 0 | Average | 157.5 | 55.13 | SF | 0 | 0.35 | Dwelling | 0 | 66.15 | 0 | Percent | 0 | Yes | 66.15 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 26 | MASTER_BEDRO | Master Bedroom | Dehumidifier (per 24 hour period) - Large - No monitoring | 0 | Average | 3 | 225 | EA | 0 | 75 | Dwelling | 0 | 270 | 0 | Percent | 0 | Yes | 270 | Yes | No | WTR | DHM> | DAVID.SO |  | 2022-01-27
FALSE | 27 | MASTER_BEDRO | Master Bedroom | Air mover (per 24 hour period) - No monitoring | 0 | Average | 6 | 201 | EA | 0 | 33.5 | Dwelling | 0 | 241.2 | 0 | Percent | 0 | Yes | 241.2 | Yes | No | WTR | DRY | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 28 | FOYER_ENTRY | Foyer/Entry | Demolish/remove - bedroom/room (up to 200 sf) | 0 | Average | 51.96 | 354.37 | SF | 0 | 6.82 | Dwelling | 0 | 425.25 | 0 | Percent | 0 | Yes | 425.25 | Yes | No | DMO | HRBDR | DAVID.SO |  | 2022-01-27
FALSE | 29 | FOYER_ENTRY | Foyer/Entry | Clean with pressure/chemical spray | 0 | Average | 51.96 | 22.86 | SF | 0 | 0.44 | Dwelling | 0 | 27.44 | 0 | Percent | 0 | Yes | 27.44 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 30 | FOYER_ENTRY | Foyer/Entry | Apply plant-based anti-microbial agent to the floor | 0 | Average | 51.96 | 18.19 | SF | 0 | 0.35 | Dwelling | 0 | 21.83 | 0 | Percent | 0 | Yes | 21.83 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 31 | BATHROOM | Bathroom | Demolish/remove - bathroom (up to 50 sf) | 0 | Average | 44.17 | 852.48 | SF | 0 | 19.3 | Dwelling | 0 | 1022.98 | 0 | Percent | 0 | Yes | 1022.98 | Yes | No | DMO | HRBR | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 32 | BATHROOM | Bathroom | Clean with pressure/chemical spray | 0 | Average | 44.17 | 19.43 | SF | 0 | 0.44 | Dwelling | 0 | 23.31 | 0 | Percent | 0 | Yes | 23.31 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 33 | BATHROOM | Bathroom | Apply plant-based anti-microbial agent to the floor | 0 | Average | 44.17 | 15.46 | SF | 0 | 0.35 | Dwelling | 0 | 18.56 | 0 | Percent | 0 | Yes | 18.56 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 34 | BATHROOM | Bathroom | Dehumidifier (per 24 hour period) - Large - No monitoring | 0 | Average | 3 | 225 | EA | 0 | 75 | Dwelling | 0 | 270 | 0 | Percent | 0 | Yes | 270 | Yes | No | WTR | DHM> | DAVID.SO |  | 2022-01-27
FALSE | 35 | BEDROOM_1 | Bedroom 1 | Demolish/remove - bedroom/room (up to 200 sf) | 0 | Average | 102.79 | 701.03 | SF | 0 | 6.82 | Dwelling | 0 | 841.23 | 0 | Percent | 0 | Yes | 841.23 | Yes | No | DMO | HRBDR | DAVID.SO |  | 2022-01-27
FALSE | 36 | BEDROOM_1 | Bedroom 1 | Clean with pressure/chemical spray | 0 | Average | 102.79 | 45.23 | SF | 0 | 0.44 | Dwelling | 0 | 54.27 | 0 | Percent | 0 | Yes | 54.27 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 37 | BEDROOM_1 | Bedroom 1 | Apply plant-based anti-microbial agent to the floor | 0 | Average | 102.79 | 35.98 | SF | 0 | 0.35 | Dwelling | 0 | 43.18 | 0 | Percent | 0 | Yes | 43.18 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 38 | BEDROOM_1 | Bedroom 1 | Dehumidifier (per 24 hour period) - Large - No monitoring | 0 | Average | 3 | 225 | EA | 0 | 75 | Dwelling | 0 | 270 | 0 | Percent | 0 | Yes | 270 | Yes | No | WTR | DHM> | DAVID.SO |  | 2022-01-27
FALSE | 39 | BEDROOM_1 | Bedroom 1 | Air mover (per 24 hour period) - No monitoring | 0 | Average | 3 | 100.5 | EA | 0 | 33.5 | Dwelling | 0 | 120.6 | 0 | Percent | 0 | Yes | 120.6 | Yes | No | WTR | DRY | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 40 | OFFICE | Office | Demolish/remove - bedroom/room (up to 200 sf) | 0 | Average | 77.29 | 527.12 | SF | 0 | 6.82 | Dwelling | 0 | 632.54 | 0 | Percent | 0 | Yes | 632.54 | Yes | No | DMO | HRBDR | DAVID.SO |  | 2022-01-27
FALSE | 41 | OFFICE | Office | Clean with pressure/chemical spray | 0 | Average | 77.29 | 34.01 | SF | 0 | 0.44 | Dwelling | 0 | 40.81 | 0 | Percent | 0 | Yes | 40.81 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 42 | OFFICE | Office | Apply plant-based anti-microbial agent to the floor | 0 | Average | 77.29 | 27.05 | SF | 0 | 0.35 | Dwelling | 0 | 32.47 | 0 | Percent | 0 | Yes | 32.47 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 43 | OFFICE | Office | Air mover (per 24 hour period) - No monitoring | 0 | Average | 3 | 100.5 | EA | 0 | 33.5 | Dwelling | 0 | 120.6 | 0 | Percent | 0 | Yes | 120.6 | Yes | No | WTR | DRY | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 44 | GARAGE | Garage | Tear out wet drywall, cleanup, bag for disposal | 0 | Average | 1112 | 1445.6 | SF | 0 | 1.3 | Dwelling | 0 | 1734.72 | 0 | Percent | 0 | Yes | 1734.72 | Yes | No | WTR | DRYW | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 45 | GARAGE | Garage | Clean with pressure/chemical spray | 0 | Average | 440 | 193.6 | SF | 0 | 0.44 | Dwelling | 0 | 232.32 | 0 | Percent | 0 | Yes | 232.32 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-22
FALSE | 46 | GARAGE | Garage | Tear out and bag wet insulation | 0 | Average | 1112 | 1056.4 | SF | 0 | 0.95 | Dwelling | 0 | 1267.68 | 0 | Percent | 0 | Yes | 1267.68 | Yes | No | WTR | INS | DAVID.SO |  | 2022-01-27
FALSE | 47 | GARAGE | Garage | Air mover (per 24 hour period) - No monitoring | 0 | Average | 15 | 502.5 | EA | 0 | 33.5 | Dwelling | 0 | 603 | 0 | Percent | 0 | Yes | 603 | Yes | No | WTR | DRY | DAVID.SO |  | 2022-01-22
FALSE | 48 | MAIN_LEVEL | Main Level | Dumpster load - Approx. 30 yards, 5-7 tons of debris | 0 | Average | 2 | 2262 | EA | 0 | 1131 | Dwelling | 0 | 2714.4 | 0 | Percent | 0 | Yes | 2714.4 | Yes | No | DMO | DUMP> | DAVID.SO |  | 2022-01-22
FALSE | 49 | MAIN_LEVEL | Main Level | Cleaning Technician - per hour | 0 | Average | 24 | 1368.96 | HR | 0 | 57.04 | Dwelling | 0 | 1642.76 | 0 | Percent | 0 | Yes | 1642.76 | Yes | No | CLN | LAB | DAVID.SO |  | 2022-01-22
FALSE | 50 | MAIN_LEVEL | Main Level | Blown-in insulation - 16" depth - R44 | 0 | Average | 1497.44 | 3818.47 | SF | 0 | 2.55 | Dwelling | 0 | 4582.17 | 150 | Percent | 0 | Yes | 4582.17 | Yes | No | INS | BI16 | DAVID.SO |  | 2022-01-27
FALSE | 51 | MAIN_LEVEL | Main Level | Taxes, insurance, permits & fees (Bid Item) | 0 | Average | 1 | 19000 | EA | 0 | 19000 | Dwelling | 0 | 22800 | 0 | Percent | 0 | Yes | 22800 | Yes | No | FEE | TIPF | ERIC.VAN |  | 2022-01-27 | Price List Item
FALSE | 52 | MAIN_LEVEL | Main Level | Exterior door, 8' - Deluxe - wood w/detail - pre-hung | 0 | Average | 1 | 3278.68 | EA | 0 | 3278.68 | Dwelling | 0 | 3934.42 | 100 | Percent | 0 | Yes | 3934.42 | Yes | No | DOR | X8+++ | DAVID.SO |  | 2022-01-31
FALSE | 53 | MAIN_LEVEL | Main Level | Exterior door - Deluxe grade - wood w/detail - pre-hung | 0 | Average | 1 | 2343.3 | EA | 0 | 2343.3 | Dwelling | 0 | 2811.96 | 100 | Percent | 0 | Yes | 2811.96 | Yes | No | DOR | X+++ | DAVID.SO |  | 2022-01-31
FALSE | 54 | MAIN_LEVEL | Main Level | Wood window - casement, 24-32 sf, Premium grade | 0 | Average | 7 | 13145.72 | EA | 0 | 1877.96 | Dwelling | 0 | 15774.86 | 30 | Percent | 0 | Yes | 15774.86 | Yes | No | WDW | C>++ | DAVID.SO |  | 2022-01-31
FALSE | 55 | MAIN_LEVEL | Main Level | Wood window - casement, 12-23 sf, Premium grade | 0 | Average | 1 | 1278.43 | EA | 0 | 1278.43 | Dwelling | 0 | 1534.11 | 30 | Percent | 0 | Yes | 1534.11 | Yes | No | WDW | C++ | DAVID.SO |  | 2022-01-31
FALSE | 56 | DINING_ROOM2 | Dining Room | 110 volt copper wiring run, box and outlet | 0 | Average | 3.32 | 292.96 | EA | 0 | 88.24 | Dwelling | 0 | 351.56 | 100 | Percent | 0 | Yes | 351.56 | Yes | No | ELE | 110 | DAVID.SO |  | 2022-01-27
FALSE | 57 | DINING_ROOM2 | Dining Room | 110 volt copper wiring run, box and switch | 0 | Average | 2 | 177.68 | EA | 0 | 88.84 | Dwelling | 0 | 213.22 | 100 | Percent | 0 | Yes | 213.22 | Yes | No | ELE | 110S | DAVID.SO |  | 2022-01-27
FALSE | 58 | DINING_ROOM2 | Dining Room | Batt insulation - 6" - R20 - unfaced batt | 0 | Average | 192 | 347.52 | SF | 0 | 1.81 | Dwelling | 0 | 417.02 | 150 | Percent | 0 | Yes | 417.02 | Yes | No | INS | BT6 | DAVID.SO |  | 2022-01-22
FALSE | 59 | DINING_ROOM2 | Dining Room | Polyethylene vapor barrier, seam taping & joint caulking | 0 | Average | 371.89 | 230.57 | SF | 0 | 0.62 | Dwelling | 0 | 276.69 | 150 | Percent | 0 | Yes | 276.69 | Yes | No | INS | VISTC | DAVID.SO |  | 2022-01-22
FALSE | 60 | DINING_ROOM2 | Dining Room | 1/2" drywall - hung, taped, floated, ready for paint | 0 | Average | 371.89 | 1253.27 | SF | 0 | 3.37 | Dwelling | 0 | 1503.93 | 150 | Percent | 0 | Yes | 1503.93 | Yes | No | DRY | 1/2 | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 61 | DINING_ROOM2 | Dining Room | Seal the walls and ceiling w/latex based stain blocker - one coat | 0 | Average | 371.89 | 397.92 | SF | 0 | 1.07 | Dwelling | 0 | 477.5 | 15 | Percent | 0 | Yes | 477.5 | Yes | No | PNT | S | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 62 | DINING_ROOM2 | Dining Room | Mask wall - plastic, paper, tape (per LF) | 0 | Average | 36.5 | 64.24 | LF | 0 | 1.76 | Dwelling | 0 | 77.08 | 150 | Percent | 0 | Yes | 77.08 | Yes | No | DRY | MASKLF | DAVID.SO |  | 2022-01-27
FALSE | 63 | DINING_ROOM2 | Dining Room | Texture drywall - smooth / skim coat | 0 | Average | 292 | 581.08 | SF | 0 | 1.99 | Dwelling | 0 | 697.3 | 150 | Percent | 0 | Yes | 697.3 | Yes | No | DRY | TEX++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 64 | DINING_ROOM2 | Dining Room | Chandelier - Premium grade | 0 | Average | 1 | 599.82 | EA | 0 | 599.82 | Dwelling | 0 | 719.78 | 20 | Percent | 0 | Yes | 719.78 | Yes | No | LIT | CHAN++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 65 | DINING_ROOM2 | Dining Room | Paint the walls and ceiling - two coats - 2 colours | 0 | Average | 371.89 | 762.37 | SF | 0 | 2.05 | Dwelling | 0 | 914.85 | 15 | Percent | 0 | Yes | 914.85 | Yes | No | PNT | P2+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 66 | DINING_ROOM2 | Dining Room | Vinyl - metal transition strip | 0 | Average | 12 | 56.4 | LF | 0 | 4.7 | Dwelling | 0 | 67.68 | 50 | Percent | 0 | Yes | 67.68 | Yes | No | FCV | EDGE | DAVID.SO |  | 2022-01-22
FALSE | 67 | DINING_ROOM2 | Dining Room | Pre-finished solid wood flooring - Premium grade | 0 | Average | 146 | 2657.2 | SF | 0 | 18.2 | Dwelling | 0 | 3188.64 | 150 | Percent | 0 | Yes | 3188.64 | Yes | No | FCW | AVPF++ | DAVID.SO |  | 2022-01-31
FALSE | 68 | DINING_ROOM2 | Dining Room | Baseboard - 5 1/4" hardwood | 0 | Average | 26.58 | 248.52 | LF | 0 | 9.35 | Dwelling | 0 | 298.22 | 150 | Percent | 0 | Yes | 298.22 | Yes | No | FNC | B5H | DAVID.SO |  | 2022-01-31
FALSE | 69 | DINING_ROOM2 | Dining Room | Finish baseboard - oversized - 1 coat urethane | 0 | Average | 26.58 | 50.24 | LF | 0 | 1.89 | Dwelling | 0 | 60.28 | 15 | Percent | 0 | Yes | 60.28 | Yes | No | PNT | BS>1 | DAVID.SO |  | 2022-01-31
FALSE | 70 | DINING_ROOM2 | Dining Room | Crown moulding - 4 1/4" stain grade | 0 | Average | 36.5 | 319.74 | LF | 0 | 8.76 | Dwelling | 0 | 383.68 | 150 | Percent | 0 | Yes | 383.68 | Yes | No | FNC | CWN>+ | DAVID.SO |  | 2022-01-31
FALSE | 71 | DINING_ROOM2 | Dining Room | Stain & finish crown moulding | 0 | Average | 36.5 | 103.66 | LF | 0 | 2.84 | Dwelling | 0 | 124.4 | 15 | Percent | 0 | Yes | 124.4 | Yes | No | PNT | CWNS | DAVID.SO |  | 2022-01-31
FALSE | 72 | DINING_ROOM2 | Dining Room | Mask and prep for paint - plastic, paper, tape (per LF) | 0 | Average | 73 | 164.25 | LF | 0 | 2.25 | Dwelling | 0 | 197.11 | 15 | Percent | 0 | Yes | 197.11 | Yes | No | PNT | MASKLF | DAVID.SO |  | 2022-01-31
FALSE | 73 | KITCHEN | Kitchen | 110 volt copper wiring run, box and outlet | 0 | Average | 3.22 | 284.13 | EA | 0 | 88.24 | Dwelling | 0 | 340.95 | 100 | Percent | 0 | Yes | 340.95 | Yes | No | ELE | 110 | DAVID.SO |  | 2022-01-27
FALSE | 74 | KITCHEN | Kitchen | 110 volt copper wiring run, box and switch | 0 | Average | 2 | 177.68 | EA | 0 | 88.84 | Dwelling | 0 | 213.22 | 100 | Percent | 0 | Yes | 213.22 | Yes | No | ELE | 110S | DAVID.SO |  | 2022-01-27
FALSE | 75 | KITCHEN | Kitchen | Batt insulation - 6" - R20 - unfaced batt | 0 | Average | 56 | 101.36 | SF | 0 | 1.81 | Dwelling | 0 | 121.64 | 150 | Percent | 0 | Yes | 121.64 | Yes | No | INS | BT6 | DAVID.SO |  | 2022-01-22
FALSE | 76 | KITCHEN | Kitchen | Polyethylene vapor barrier, seam taping & joint caulking | 0 | Average | 310 | 192.2 | SF | 0 | 0.62 | Dwelling | 0 | 230.64 | 150 | Percent | 0 | Yes | 230.64 | Yes | No | INS | VISTC | DAVID.SO |  | 2022-01-22
FALSE | 77 | KITCHEN | Kitchen | 1/2" drywall - hung, taped, floated, ready for paint | 0 | Average | 310 | 1044.7 | SF | 0 | 3.37 | Dwelling | 0 | 1253.64 | 150 | Percent | 0 | Yes | 1253.64 | Yes | No | DRY | 1/2 | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 78 | KITCHEN | Kitchen | Mask wall - plastic, paper, tape (per LF) | 0 | Average | 38.5 | 67.76 | LF | 0 | 1.76 | Dwelling | 0 | 81.32 | 150 | Percent | 0 | Yes | 81.32 | Yes | No | DRY | MASKLF | DAVID.SO |  | 2022-01-31
FALSE | 79 | KITCHEN | Kitchen | Texture drywall - smooth / skim coat | 0 | Average | 174 | 346.26 | SF | 0 | 1.99 | Dwelling | 0 | 415.52 | 150 | Percent | 0 | Yes | 415.52 | Yes | No | DRY | TEX++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 80 | KITCHEN | Kitchen | Seal/prime then paint the ceiling twice (3 coats) - 2 colours | 0 | Average | 87 | 233.16 | SF | 0 | 2.68 | Dwelling | 0 | 279.8 | 15 | Percent | 0 | Yes | 279.8 | Yes | No | PNT | SP2+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 81 | KITCHEN | Kitchen | Cabinetry - lower (base) units - Premium grade | 0 | Average | 28 | 11634.56 | LF | 0 | 415.52 | Dwelling | 0 | 13961.48 | 50 | Percent | 0 | Yes | 13961.48 | Yes | No | CAB | LOW++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 82 | KITCHEN | Kitchen | Countertop - solid surface/granite - Reset | 0 | Average | 56 | 1044.96 | SF | 0 | 18.66 | Dwelling | 0 | 1253.96 | 0 | Percent | 0 | Yes | 1253.96 | Yes | No | CAB | CTSSR | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 83 | KITCHEN | Kitchen | Cabinetry - upper (wall) units - Premium grade | 0 | Average | 21 | 7077.63 | LF | 0 | 337.03 | Dwelling | 0 | 8493.15 | 50 | Percent | 0 | Yes | 8493.15 | Yes | No | CAB | UP++ | DAVID.SO |  | 2022-01-31
FALSE | 84 | KITCHEN | Kitchen | Sink faucet - Kitchen - Premium grade | 0 | Average | 1 | 586.97 | EA | 0 | 586.97 | Dwelling | 0 | 704.37 | 15 | Percent | 0 | Yes | 704.37 | Yes | No | PLM | FAU++ | DAVID.SO |  | 2022-01-22
FALSE | 85 | KITCHEN | Kitchen | Sink - double basin - Premium grade | 0 | Average | 1 | 812.28 | EA | 0 | 812.28 | Dwelling | 0 | 974.74 | 50 | Percent | 0 | Yes | 974.74 | Yes | No | PLM | SNKD++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 86 | KITCHEN | Kitchen | Dishwasher connection | 0 | Average | 1 | 158.28 | EA | 0 | 158.28 | Dwelling | 0 | 189.94 | 100 | Percent | 0 | Yes | 189.94 | Yes | No | PLM | DW | DAVID.SO |  | 2022-01-22
FALSE | 87 | KITCHEN | Kitchen | Refrigerator/icemaker water supply box with valve | 0 | Average | 1 | 153.44 | EA | 0 | 153.44 | Dwelling | 0 | 184.12 | 20 | Percent | 0 | Yes | 184.12 | Yes | No | PLM | WSBOX | DAVID.SO |  | 2022-01-22
FALSE | 88 | KITCHEN | Kitchen | Light fixture - Premium grade | 0 | Average | 2 | 388 | EA | 0 | 194 | Dwelling | 0 | 465.6 | 20 | Percent | 0 | Yes | 465.6 | Yes | No | LIT | AV++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 89 | KITCHEN | Kitchen | Hanging double light fixture - Premium grade | 0 | Average | 1 | 234.32 | EA | 0 | 234.32 | Dwelling | 0 | 281.18 | 20 | Percent | 0 | Yes | 281.18 | Yes | No | LIT | HG2++ | DAVID.SO |  | 2022-02-07
FALSE | 90 | KITCHEN | Kitchen | Underlayment - sound/crack membrane - up to 40 mil | 0 | Average | 87 | 241.86 | SF | 0 | 2.78 | Dwelling | 0 | 290.24 | 15 | Percent | 0 | Yes | 290.24 | Yes | No | FCT | US | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 91 | KITCHEN | Kitchen | Tile floor covering - Premium grade | 0 | Average | 87 | 1825.26 | SF | 0 | 20.98 | Dwelling | 0 | 2190.32 | 100 | Percent | 0 | Yes | 2190.32 | Yes | No | FCT | AV++ | DAVID.SO |  | 2022-01-31
FALSE | 92 | KITCHEN | Kitchen | Vinyl - metal transition strip | 0 | Average | 3 | 14.1 | LF | 0 | 4.7 | Dwelling | 0 | 16.92 | 50 | Percent | 0 | Yes | 16.92 | Yes | No | FCV | EDGE | DAVID.SO |  | 2022-01-22
FALSE | 93 | KITCHEN | Kitchen | Baseboard - 5 1/4" hardwood | 0 | Average | 25.75 | 240.76 | LF | 0 | 9.35 | Dwelling | 0 | 288.92 | 150 | Percent | 0 | Yes | 288.92 | Yes | No | FNC | B5H | DAVID.SO |  | 2022-01-31
FALSE | 94 | KITCHEN | Kitchen | Finish baseboard - oversized - 1 coat urethane | 0 | Average | 25.75 | 48.67 | LF | 0 | 1.89 | Dwelling | 0 | 58.41 | 15 | Percent | 0 | Yes | 58.41 | Yes | No | PNT | BS>1 | DAVID.SO |  | 2022-01-31
FALSE | 95 | KITCHEN | Kitchen | Crown moulding - 4 1/4" stain grade | 0 | Average | 38.5 | 337.26 | LF | 0 | 8.76 | Dwelling | 0 | 404.72 | 150 | Percent | 0 | Yes | 404.72 | Yes | No | FNC | CWN>+ | DAVID.SO |  | 2022-01-31
FALSE | 96 | KITCHEN | Kitchen | Stain & finish crown moulding | 0 | Average | 38.5 | 109.34 | LF | 0 | 2.84 | Dwelling | 0 | 131.2 | 15 | Percent | 0 | Yes | 131.2 | Yes | No | PNT | CWNS | DAVID.SO |  | 2022-01-31
FALSE | 97 | KITCHEN | Kitchen | Mask and prep for paint - plastic, paper, tape (per LF) | 0 | Average | 77 | 173.25 | LF | 0 | 2.25 | Dwelling | 0 | 207.91 | 15 | Percent | 0 | Yes | 207.91 | Yes | No | PNT | MASKLF | DAVID.SO |  | 2022-01-31
FALSE | 98 | KITCHEN | Kitchen | Range - electric - Remove & reset | 0 | Average | 0.5 | 22.39 | EA | 0 | 44.77 | Dwelling | 0 | 26.87 | 0 | Percent | 0 | Yes | 26.87 | Yes | No | APP | RGRS | DAVID.SO |  | 2022-01-22
FALSE | 99 | KITCHEN | Kitchen | Dishwasher - Detach & reset | 0 | Average | 0.5 | 123.07 | EA | 0 | 246.14 | Dwelling | 0 | 147.69 | 0 | Percent | 0 | Yes | 147.69 | Yes | No | APP | DWRS | DAVID.SO |  | 2022-01-22
FALSE | 100 | KITCHEN | Kitchen | Refrigerator - Remove & reset | 0 | Average | 0.5 | 29.84 | EA | 0 | 59.68 | Dwelling | 0 | 35.8 | 0 | Percent | 0 | Yes | 35.8 | Yes | No | APP | RFRS | DAVID.SO |  | 2022-01-22
FALSE | 101 | LIVING_ROOM | Living Room | 110 volt copper wiring run, box and outlet | 0 | Average | 3.38 | 298.25 | EA | 0 | 88.24 | Dwelling | 0 | 357.91 | 100 | Percent | 0 | Yes | 357.91 | Yes | No | ELE | 110 | DAVID.SO |  | 2022-01-27
FALSE | 102 | LIVING_ROOM | Living Room | 110 volt copper wiring run, box and switch | 0 | Average | 2 | 177.68 | EA | 0 | 88.84 | Dwelling | 0 | 213.22 | 100 | Percent | 0 | Yes | 213.22 | Yes | No | ELE | 110S | DAVID.SO |  | 2022-01-27
FALSE | 103 | LIVING_ROOM | Living Room | Batt insulation - 6" - R20 - unfaced batt | 0 | Average | 192 | 347.52 | SF | 0 | 1.81 | Dwelling | 0 | 417.02 | 150 | Percent | 0 | Yes | 417.02 | Yes | No | INS | BT6 | DAVID.SO |  | 2022-01-22
FALSE | 104 | LIVING_ROOM | Living Room | Polyethylene vapor barrier, seam taping & joint caulking | 0 | Average | 379 | 234.98 | SF | 0 | 0.62 | Dwelling | 0 | 281.98 | 150 | Percent | 0 | Yes | 281.98 | Yes | No | INS | VISTC | DAVID.SO |  | 2022-01-22
FALSE | 105 | LIVING_ROOM | Living Room | 1/2" drywall - hung, taped, floated, ready for paint | 0 | Average | 379 | 1277.23 | SF | 0 | 3.37 | Dwelling | 0 | 1532.67 | 150 | Percent | 0 | Yes | 1532.67 | Yes | No | DRY | 1/2 | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 106 | LIVING_ROOM | Living Room | Seal the walls and ceiling w/latex based stain blocker - one coat | 0 | Average | 379 | 405.53 | SF | 0 | 1.07 | Dwelling | 0 | 486.63 | 15 | Percent | 0 | Yes | 486.63 | Yes | No | PNT | S | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 107 | LIVING_ROOM | Living Room | Mask wall - plastic, paper, tape (per LF) | 0 | Average | 27 | 47.52 | LF | 0 | 1.76 | Dwelling | 0 | 57.02 | 150 | Percent | 0 | Yes | 57.02 | Yes | No | DRY | MASKLF | DAVID.SO |  | 2022-01-27
FALSE | 108 | LIVING_ROOM | Living Room | Texture drywall - smooth / skim coat | 0 | Average | 326 | 648.74 | SF | 0 | 1.99 | Dwelling | 0 | 778.48 | 150 | Percent | 0 | Yes | 778.48 | Yes | No | DRY | TEX++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 109 | LIVING_ROOM | Living Room | Light fixture - Premium grade | 0 | Average | 1 | 194 | EA | 0 | 194 | Dwelling | 0 | 232.8 | 20 | Percent | 0 | Yes | 232.8 | Yes | No | LIT | AV++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 110 | LIVING_ROOM | Living Room | Paint the walls and ceiling - two coats - 2 colours | 0 | Average | 379 | 776.95 | SF | 0 | 2.05 | Dwelling | 0 | 932.35 | 15 | Percent | 0 | Yes | 932.35 | Yes | No | PNT | P2+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 111 | LIVING_ROOM | Living Room | Pre-finished solid wood flooring - Premium grade | 0 | Average | 163 | 2966.6 | SF | 0 | 18.2 | Dwelling | 0 | 3559.92 | 150 | Percent | 0 | Yes | 3559.92 | Yes | No | FCW | AVPF++ | DAVID.SO |  | 2022-01-31
FALSE | 112 | LIVING_ROOM | Living Room | Baseboard - 5 1/4" hardwood | 0 | Average | 27 | 252.45 | LF | 0 | 9.35 | Dwelling | 0 | 302.95 | 150 | Percent | 0 | Yes | 302.95 | Yes | No | FNC | B5H | DAVID.SO |  | 2022-01-31
FALSE | 113 | LIVING_ROOM | Living Room | Finish baseboard - oversized - 1 coat urethane | 0 | Average | 27 | 51.03 | LF | 0 | 1.89 | Dwelling | 0 | 61.23 | 15 | Percent | 0 | Yes | 61.23 | Yes | No | PNT | BS>1 | DAVID.SO |  | 2022-01-31
FALSE | 114 | LIVING_ROOM | Living Room | Crown moulding - 4 1/4" stain grade | 0 | Average | 27 | 236.52 | LF | 0 | 8.76 | Dwelling | 0 | 283.82 | 150 | Percent | 0 | Yes | 283.82 | Yes | No | FNC | CWN>+ | DAVID.SO |  | 2022-01-31
FALSE | 115 | LIVING_ROOM | Living Room | Stain & finish crown moulding | 0 | Average | 27 | 76.68 | LF | 0 | 2.84 | Dwelling | 0 | 92.02 | 15 | Percent | 0 | Yes | 92.02 | Yes | No | PNT | CWNS | DAVID.SO |  | 2022-01-31
FALSE | 116 | LIVING_ROOM | Living Room | Mask and prep for paint - plastic, paper, tape (per LF) | 0 | Average | 54 | 121.5 | LF | 0 | 2.25 | Dwelling | 0 | 145.8 | 15 | Percent | 0 | Yes | 145.8 | Yes | No | PNT | MASKLF | DAVID.SO |  | 2022-01-31
FALSE | 117 | HALLWAY2 | Hallway | 110 volt copper wiring run, box and outlet | 0 | Average | 9.43 | 832.1 | EA | 0 | 88.24 | Dwelling | 0 | 998.52 | 100 | Percent | 0 | Yes | 998.52 | Yes | No | ELE | 110 | DAVID.SO |  | 2022-01-27
FALSE | 118 | HALLWAY2 | Hallway | 110 volt copper wiring run, box and switch | 0 | Average | 5 | 444.2 | EA | 0 | 88.84 | Dwelling | 0 | 533.04 | 100 | Percent | 0 | Yes | 533.04 | Yes | No | ELE | 110S | DAVID.SO |  | 2022-01-27
FALSE | 119 | HALLWAY2 | Hallway | 1/2" drywall - hung, taped, floated, ready for paint | 0 | Average | 717.61 | 2418.35 | SF | 0 | 3.37 | Dwelling | 0 | 2902.03 | 150 | Percent | 0 | Yes | 2902.03 | Yes | No | DRY | 1/2 | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 120 | HALLWAY2 | Hallway | Seal the walls and ceiling w/latex based stain blocker - one coat | 0 | Average | 717.61 | 767.84 | SF | 0 | 1.07 | Dwelling | 0 | 921.4 | 15 | Percent | 0 | Yes | 921.4 | Yes | No | PNT | S | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 121 | HALLWAY2 | Hallway | Mask wall - plastic, paper, tape (per LF) | 0 | Average | 78.25 | 137.72 | LF | 0 | 1.76 | Dwelling | 0 | 165.26 | 150 | Percent | 0 | Yes | 165.26 | Yes | No | DRY | MASKLF | DAVID.SO |  | 2022-01-27
FALSE | 122 | HALLWAY2 | Hallway | Texture drywall - smooth / skim coat | 0 | Average | 221 | 439.79 | SF | 0 | 1.99 | Dwelling | 0 | 527.75 | 150 | Percent | 0 | Yes | 527.75 | Yes | No | DRY | TEX++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 123 | HALLWAY2 | Hallway | Light fixture - Premium grade | 0 | Average | 2 | 388 | EA | 0 | 194 | Dwelling | 0 | 465.6 | 20 | Percent | 0 | Yes | 465.6 | Yes | No | LIT | AV++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 124 | HALLWAY2 | Hallway | Paint the walls and ceiling - two coats - 2 colours | 0 | Average | 717.61 | 1471.1 | SF | 0 | 2.05 | Dwelling | 0 | 1765.32 | 15 | Percent | 0 | Yes | 1765.32 | Yes | No | PNT | P2+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 125 | HALLWAY2 | Hallway | Interior door unit - Premium grade | 0 | Average | 6 | 3243.78 | EA | 0 | 540.63 | Dwelling | 0 | 3892.54 | 100 | Percent | 0 | Yes | 3892.54 | Yes | No | DOR | AV++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 126 | HALLWAY2 | Hallway | Stain & finish door slab only (per side) | 0 | Average | 12 | 1178.28 | EA | 0 | 98.19 | Dwelling | 0 | 1413.94 | 15 | Percent | 0 | Yes | 1413.94 | Yes | No | PNT | DORS | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 127 | HALLWAY2 | Hallway | Add. cost to pre-stain door/window trim & jamb (per side) | 0 | Average | 12 | 282.84 | EA | 0 | 23.57 | Dwelling | 0 | 339.4 | 15 | Percent | 0 | Yes | 339.4 | Yes | No | PNT | DORTP | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 128 | HALLWAY2 | Hallway | Door knob - interior - Premium grade | 0 | Average | 6 | 546.24 | EA | 0 | 91.04 | Dwelling | 0 | 655.48 | 20 | Percent | 0 | Yes | 655.48 | Yes | No | FNH | DORH++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 129 | HALLWAY2 | Hallway | Pre-finished solid wood flooring - Premium grade | 0 | Average | 110.5 | 2011.1 | SF | 0 | 18.2 | Dwelling | 0 | 2413.32 | 150 | Percent | 0 | Yes | 2413.32 | Yes | No | FCW | AVPF++ | DAVID.SO |  | 2022-01-31
FALSE | 130 | HALLWAY2 | Hallway | Baseboard - 5 1/4" hardwood | 0 | Average | 75.42 | 705.18 | LF | 0 | 9.35 | Dwelling | 0 | 846.22 | 150 | Percent | 0 | Yes | 846.22 | Yes | No | FNC | B5H | DAVID.SO |  | 2022-01-31
FALSE | 131 | HALLWAY2 | Hallway | Finish baseboard - oversized - 1 coat urethane | 0 | Average | 75.42 | 142.54 | LF | 0 | 1.89 | Dwelling | 0 | 171.04 | 15 | Percent | 0 | Yes | 171.04 | Yes | No | PNT | BS>1 | DAVID.SO |  | 2022-01-31
FALSE | 132 | HALLWAY2 | Hallway | Crown moulding - 4 1/4" stain grade | 0 | Average | 78.25 | 685.47 | LF | 0 | 8.76 | Dwelling | 0 | 822.57 | 150 | Percent | 0 | Yes | 822.57 | Yes | No | FNC | CWN>+ | DAVID.SO |  | 2022-01-31
FALSE | 133 | HALLWAY2 | Hallway | Stain & finish crown moulding | 0 | Average | 78.25 | 222.23 | LF | 0 | 2.84 | Dwelling | 0 | 266.67 | 15 | Percent | 0 | Yes | 266.67 | Yes | No | PNT | CWNS | DAVID.SO |  | 2022-01-31
FALSE | 134 | HALLWAY2 | Hallway | Mask and prep for paint - plastic, paper, tape (per LF) | 0 | Average | 156.5 | 352.13 | LF | 0 | 2.25 | Dwelling | 0 | 422.55 | 15 | Percent | 0 | Yes | 422.55 | Yes | No | PNT | MASKLF | DAVID.SO |  | 2022-01-31
FALSE | 135 | BEDROOM_4 | Bedroom 2 | 110 volt copper wiring run, box and outlet | 0 | Average | 7.5 | 661.8 | EA | 0 | 88.24 | Dwelling | 0 | 794.16 | 100 | Percent | 0 | Yes | 794.16 | Yes | No | ELE | 110 | DAVID.SO |  | 2022-01-27
FALSE | 136 | BEDROOM_4 | Bedroom 2 | 110 volt copper wiring run, box and switch | 0 | Average | 1 | 88.84 | EA | 0 | 88.84 | Dwelling | 0 | 106.6 | 100 | Percent | 0 | Yes | 106.6 | Yes | No | ELE | 110S | DAVID.SO |  | 2022-01-27
FALSE | 137 | BEDROOM_4 | Bedroom 2 | Batt insulation - 6" - R20 - unfaced batt | 0 | Average | 80 | 144.8 | SF | 0 | 1.81 | Dwelling | 0 | 173.76 | 150 | Percent | 0 | Yes | 173.76 | Yes | No | INS | BT6 | DAVID.SO |  | 2022-01-22
FALSE | 138 | BEDROOM_4 | Bedroom 2 | Polyethylene vapor barrier, seam taping & joint caulking | 0 | Average | 597.43 | 370.41 | SF | 0 | 0.62 | Dwelling | 0 | 444.49 | 150 | Percent | 0 | Yes | 444.49 | Yes | No | INS | VISTC | DAVID.SO |  | 2022-01-22
FALSE | 139 | BEDROOM_4 | Bedroom 2 | 1/2" drywall - hung, taped, floated, ready for paint | 0 | Average | 597.43 | 2013.34 | SF | 0 | 3.37 | Dwelling | 0 | 2416 | 150 | Percent | 0 | Yes | 2416 | Yes | No | DRY | 1/2 | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 140 | BEDROOM_4 | Bedroom 2 | Seal the walls and ceiling w/latex based stain blocker - one coat | 0 | Average | 597.43 | 639.25 | SF | 0 | 1.07 | Dwelling | 0 | 767.11 | 15 | Percent | 0 | Yes | 767.11 | Yes | No | PNT | S | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 141 | BEDROOM_4 | Bedroom 2 | Mask wall - plastic, paper, tape (per LF) | 0 | Average | 60.03 | 105.65 | LF | 0 | 1.76 | Dwelling | 0 | 126.79 | 150 | Percent | 0 | Yes | 126.79 | Yes | No | DRY | MASKLF | DAVID.SO |  | 2022-01-27
FALSE | 142 | BEDROOM_4 | Bedroom 2 | Texture drywall - smooth / skim coat | 0 | Average | 234.44 | 466.54 | SF | 0 | 1.99 | Dwelling | 0 | 559.84 | 150 | Percent | 0 | Yes | 559.84 | Yes | No | DRY | TEX++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 143 | BEDROOM_4 | Bedroom 2 | Light fixture - Premium grade | 0 | Average | 1 | 194 | EA | 0 | 194 | Dwelling | 0 | 232.8 | 20 | Percent | 0 | Yes | 232.8 | Yes | No | LIT | AV++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 144 | BEDROOM_4 | Bedroom 2 | Paint the walls and ceiling - two coats - 2 colours | 0 | Average | 597.43 | 1224.73 | SF | 0 | 2.05 | Dwelling | 0 | 1469.67 | 15 | Percent | 0 | Yes | 1469.67 | Yes | No | PNT | P2+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 145 | BEDROOM_4 | Bedroom 2 | Pre-finished solid wood flooring - Premium grade | 0 | Average | 117.22 | 2133.4 | SF | 0 | 18.2 | Dwelling | 0 | 2560.08 | 150 | Percent | 0 | Yes | 2560.08 | Yes | No | FCW | AVPF++ | DAVID.SO |  | 2022-01-31
FALSE | 146 | BEDROOM_4 | Bedroom 2 | Baseboard - 5 1/4" hardwood | 0 | Average | 60.03 | 561.28 | LF | 0 | 9.35 | Dwelling | 0 | 673.54 | 150 | Percent | 0 | Yes | 673.54 | Yes | No | FNC | B5H | DAVID.SO |  | 2022-01-31
FALSE | 147 | BEDROOM_4 | Bedroom 2 | Finish baseboard - oversized - 1 coat urethane | 0 | Average | 60.03 | 113.46 | LF | 0 | 1.89 | Dwelling | 0 | 136.16 | 15 | Percent | 0 | Yes | 136.16 | Yes | No | PNT | BS>1 | DAVID.SO |  | 2022-01-31
FALSE | 148 | BEDROOM_4 | Bedroom 2 | Bifold mirrored door set - High grade - Double | 0 | Average | 1 | 899.75 | EA | 0 | 899.75 | Dwelling | 0 | 1079.71 | 100 | Percent | 0 | Yes | 1079.71 | Yes | No | DOR | BFMIR+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 149 | BEDROOM_4 | Bedroom 2 | Door opening (jamb & casing) - 36"to60"wide - paint grade | 0 | Average | 1 | 244.82 | EA | 0 | 244.82 | Dwelling | 0 | 293.78 | 150 | Percent | 0 | Yes | 293.78 | Yes | No | FNC | DOP> | DAVID.SO |  | 2022-01-22
FALSE | 150 | BEDROOM_4 | Bedroom 2 | Paint door or window opening - Large - 2 coats (per side) | 0 | Average | 1 | 62.64 | EA | 0 | 62.64 | Dwelling | 0 | 75.16 | 15 | Percent | 0 | Yes | 75.16 | Yes | No | PNT | OP> | DAVID.SO |  | 2022-01-22
FALSE | 151 | BEDROOM_4 | Bedroom 2 | Crown moulding - 4 1/4" stain grade | 0 | Average | 60.03 | 525.86 | LF | 0 | 8.76 | Dwelling | 0 | 631.04 | 150 | Percent | 0 | Yes | 631.04 | Yes | No | FNC | CWN>+ | DAVID.SO |  | 2022-01-31
FALSE | 152 | BEDROOM_4 | Bedroom 2 | Stain & finish crown moulding | 0 | Average | 60.03 | 170.49 | LF | 0 | 2.84 | Dwelling | 0 | 204.59 | 15 | Percent | 0 | Yes | 204.59 | Yes | No | PNT | CWNS | DAVID.SO |  | 2022-01-31
FALSE | 153 | BEDROOM_4 | Bedroom 2 | Mask and prep for paint - plastic, paper, tape (per LF) | 0 | Average | 120.05 | 270.11 | LF | 0 | 2.25 | Dwelling | 0 | 324.13 | 15 | Percent | 0 | Yes | 324.13 | Yes | No | PNT | MASKLF | DAVID.SO |  | 2022-01-31
FALSE | 154 | BEDROOM_4 | Bedroom 2 | Closet Organizer - Melamine - Premium grade | 0 | Average | 5 | 978.7 | LF | 0 | 195.74 | Dwelling | 0 | 1174.44 | 150 | Percent | 0 | Yes | 1174.44 | Yes | No | FNC | CLOSM++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 155 | MASTER_BEDRO | Master Bedroom | 110 volt copper wiring run, box and outlet | 0 | Average | 8.04 | 709.45 | EA | 0 | 88.24 | Dwelling | 0 | 851.35 | 100 | Percent | 0 | Yes | 851.35 | Yes | No | ELE | 110 | DAVID.SO |  | 2022-01-27
FALSE | 156 | MASTER_BEDRO | Master Bedroom | 110 volt copper wiring run, box and switch | 0 | Average | 1 | 88.84 | EA | 0 | 88.84 | Dwelling | 0 | 106.6 | 100 | Percent | 0 | Yes | 106.6 | Yes | No | ELE | 110S | DAVID.SO |  | 2022-01-27
FALSE | 157 | MASTER_BEDRO | Master Bedroom | Batt insulation - 6" - R20 - unfaced batt | 0 | Average | 208 | 376.48 | SF | 0 | 1.81 | Dwelling | 0 | 451.78 | 150 | Percent | 0 | Yes | 451.78 | Yes | No | INS | BT6 | DAVID.SO |  | 2022-01-22
FALSE | 158 | MASTER_BEDRO | Master Bedroom | Polyethylene vapor barrier, seam taping & joint caulking | 0 | Average | 672.17 | 416.75 | SF | 0 | 0.62 | Dwelling | 0 | 500.11 | 150 | Percent | 0 | Yes | 500.11 | Yes | No | INS | VISTC | DAVID.SO |  | 2022-01-22
FALSE | 159 | MASTER_BEDRO | Master Bedroom | 1/2" drywall - hung, taped, floated, ready for paint | 0 | Average | 672.17 | 2265.21 | SF | 0 | 3.37 | Dwelling | 0 | 2718.25 | 150 | Percent | 0 | Yes | 2718.25 | Yes | No | DRY | 1/2 | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 160 | MASTER_BEDRO | Master Bedroom | Seal the walls and ceiling w/latex based stain blocker - one coat | 0 | Average | 672.17 | 719.22 | SF | 0 | 1.07 | Dwelling | 0 | 863.06 | 15 | Percent | 0 | Yes | 863.06 | Yes | No | PNT | S | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 161 | MASTER_BEDRO | Master Bedroom | Mask wall - plastic, paper, tape (per LF) | 0 | Average | 64.33 | 113.22 | LF | 0 | 1.76 | Dwelling | 0 | 135.86 | 150 | Percent | 0 | Yes | 135.86 | Yes | No | DRY | MASKLF | DAVID.SO |  | 2022-01-27
FALSE | 162 | MASTER_BEDRO | Master Bedroom | Texture drywall - smooth / skim coat | 0 | Average | 315 | 626.85 | SF | 0 | 1.99 | Dwelling | 0 | 752.23 | 150 | Percent | 0 | Yes | 752.23 | Yes | No | DRY | TEX++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 163 | MASTER_BEDRO | Master Bedroom | Light fixture - Premium grade | 0 | Average | 1 | 194 | EA | 0 | 194 | Dwelling | 0 | 232.8 | 20 | Percent | 0 | Yes | 232.8 | Yes | No | LIT | AV++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 164 | MASTER_BEDRO | Master Bedroom | Paint the walls and ceiling - two coats - 2 colours | 0 | Average | 672.17 | 1377.95 | SF | 0 | 2.05 | Dwelling | 0 | 1653.55 | 15 | Percent | 0 | Yes | 1653.55 | Yes | No | PNT | P2+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 165 | MASTER_BEDRO | Master Bedroom | Pre-finished solid wood flooring - Premium grade | 0 | Average | 157.5 | 2866.5 | SF | 0 | 18.2 | Dwelling | 0 | 3439.8 | 150 | Percent | 0 | Yes | 3439.8 | Yes | No | FCW | AVPF++ | DAVID.SO |  | 2022-01-31
FALSE | 166 | MASTER_BEDRO | Master Bedroom | Baseboard - 5 1/4" hardwood | 0 | Average | 64.33 | 601.49 | LF | 0 | 9.35 | Dwelling | 0 | 721.79 | 150 | Percent | 0 | Yes | 721.79 | Yes | No | FNC | B5H | DAVID.SO |  | 2022-01-31
FALSE | 167 | MASTER_BEDRO | Master Bedroom | Finish baseboard - oversized - 1 coat urethane | 0 | Average | 64.33 | 121.58 | LF | 0 | 1.89 | Dwelling | 0 | 145.9 | 15 | Percent | 0 | Yes | 145.9 | Yes | No | PNT | BS>1 | DAVID.SO |  | 2022-01-31
FALSE | 168 | MASTER_BEDRO | Master Bedroom | Bifold mirrored door set - High grade - Double | 0 | Average | 1 | 899.75 | EA | 0 | 899.75 | Dwelling | 0 | 1079.71 | 100 | Percent | 0 | Yes | 1079.71 | Yes | No | DOR | BFMIR+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 169 | MASTER_BEDRO | Master Bedroom | Door opening (jamb & casing) - 36"to60"wide - paint grade | 0 | Average | 1 | 244.82 | EA | 0 | 244.82 | Dwelling | 0 | 293.78 | 150 | Percent | 0 | Yes | 293.78 | Yes | No | FNC | DOP> | DAVID.SO |  | 2022-01-22
FALSE | 170 | MASTER_BEDRO | Master Bedroom | Paint door or window opening - Large - 2 coats (per side) | 0 | Average | 1 | 62.64 | EA | 0 | 62.64 | Dwelling | 0 | 75.16 | 15 | Percent | 0 | Yes | 75.16 | Yes | No | PNT | OP> | DAVID.SO |  | 2022-01-22
FALSE | 171 | MASTER_BEDRO | Master Bedroom | Crown moulding - 4 1/4" stain grade | 0 | Average | 64.33 | 563.53 | LF | 0 | 8.76 | Dwelling | 0 | 676.23 | 150 | Percent | 0 | Yes | 676.23 | Yes | No | FNC | CWN>+ | DAVID.SO |  | 2022-01-31
FALSE | 172 | MASTER_BEDRO | Master Bedroom | Stain & finish crown moulding | 0 | Average | 64.33 | 182.7 | LF | 0 | 2.84 | Dwelling | 0 | 219.24 | 15 | Percent | 0 | Yes | 219.24 | Yes | No | PNT | CWNS | DAVID.SO |  | 2022-01-31
FALSE | 173 | MASTER_BEDRO | Master Bedroom | Mask and prep for paint - plastic, paper, tape (per LF) | 0 | Average | 128.67 | 289.51 | LF | 0 | 2.25 | Dwelling | 0 | 347.41 | 15 | Percent | 0 | Yes | 347.41 | Yes | No | PNT | MASKLF | DAVID.SO |  | 2022-01-31
FALSE | 174 | MASTER_BEDRO | Master Bedroom | Closet Organizer - Melamine - Premium grade | 0 | Average | 5 | 978.7 | LF | 0 | 195.74 | Dwelling | 0 | 1174.44 | 150 | Percent | 0 | Yes | 1174.44 | Yes | No | FNC | CLOSM++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 175 | FOYER_ENTRY2 | Foyer/Entry | 110 volt copper wiring run, box and outlet | 0 | Average | 3.91 | 345.02 | EA | 0 | 88.24 | Dwelling | 0 | 414.02 | 100 | Percent | 0 | Yes | 414.02 | Yes | No | ELE | 110 | DAVID.SO |  | 2022-01-27
FALSE | 176 | FOYER_ENTRY2 | Foyer/Entry | 110 volt copper wiring run, box and switch | 0 | Average | 5 | 444.2 | EA | 0 | 88.84 | Dwelling | 0 | 533.04 | 100 | Percent | 0 | Yes | 533.04 | Yes | No | ELE | 110S | DAVID.SO |  | 2022-02-07
FALSE | 177 | FOYER_ENTRY2 | Foyer/Entry | Batt insulation - 6" - R20 - unfaced batt | 0 | Average | 48 | 86.88 | SF | 0 | 1.81 | Dwelling | 0 | 104.26 | 150 | Percent | 0 | Yes | 104.26 | Yes | No | INS | BT6 | DAVID.SO |  | 2022-01-22
FALSE | 178 | FOYER_ENTRY2 | Foyer/Entry | Polyethylene vapor barrier, seam taping & joint caulking | 0 | Average | 99.97 | 61.98 | SF | 0 | 0.62 | Dwelling | 0 | 74.38 | 150 | Percent | 0 | Yes | 74.38 | Yes | No | INS | VISTC | DAVID.SO |  | 2022-01-22
FALSE | 179 | FOYER_ENTRY2 | Foyer/Entry | 1/2" drywall - hung, taped, floated, ready for paint | 0 | Average | 301.97 | 1017.64 | SF | 0 | 3.37 | Dwelling | 0 | 1221.16 | 150 | Percent | 0 | Yes | 1221.16 | Yes | No | DRY | 1/2 | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 180 | FOYER_ENTRY2 | Foyer/Entry | Seal the walls and ceiling w/latex based stain blocker - one coat | 0 | Average | 301.97 | 323.11 | SF | 0 | 1.07 | Dwelling | 0 | 387.73 | 15 | Percent | 0 | Yes | 387.73 | Yes | No | PNT | S | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 181 | FOYER_ENTRY2 | Foyer/Entry | Mask wall - plastic, paper, tape (per LF) | 0 | Average | 31.25 | 55 | LF | 0 | 1.76 | Dwelling | 0 | 66 | 150 | Percent | 0 | Yes | 66 | Yes | No | DRY | MASKLF | DAVID.SO |  | 2022-01-27
FALSE | 182 | FOYER_ENTRY2 | Foyer/Entry | Texture drywall - smooth / skim coat | 0 | Average | 103.94 | 206.84 | SF | 0 | 1.99 | Dwelling | 0 | 248.2 | 150 | Percent | 0 | Yes | 248.2 | Yes | No | DRY | TEX++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 183 | FOYER_ENTRY2 | Foyer/Entry | Chandelier - High grade | 0 | Average | 1 | 404.96 | EA | 0 | 404.96 | Dwelling | 0 | 485.96 | 20 | Percent | 0 | Yes | 485.96 | Yes | No | LIT | CHAN+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 184 | FOYER_ENTRY2 | Foyer/Entry | Paint the walls and ceiling - two coats - 2 colours | 0 | Average | 301.97 | 619.04 | SF | 0 | 2.05 | Dwelling | 0 | 742.84 | 15 | Percent | 0 | Yes | 742.84 | Yes | No | PNT | P2+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 185 | FOYER_ENTRY2 | Foyer/Entry | Pre-finished solid wood flooring - Premium grade | 0 | Average | 51.97 | 945.85 | SF | 0 | 18.2 | Dwelling | 0 | 1135.03 | 150 | Percent | 0 | Yes | 1135.03 | Yes | No | FCW | AVPF++ | DAVID.SO |  | 2022-01-31
FALSE | 186 | FOYER_ENTRY2 | Foyer/Entry | Baseboard - 5 1/4" hardwood | 0 | Average | 31.25 | 292.19 | LF | 0 | 9.35 | Dwelling | 0 | 350.63 | 150 | Percent | 0 | Yes | 350.63 | Yes | No | FNC | B5H | DAVID.SO |  | 2022-01-31
FALSE | 187 | FOYER_ENTRY2 | Foyer/Entry | Finish baseboard - oversized - 1 coat urethane | 0 | Average | 31.25 | 59.06 | LF | 0 | 1.89 | Dwelling | 0 | 70.88 | 15 | Percent | 0 | Yes | 70.88 | Yes | No | PNT | BS>1 | DAVID.SO |  | 2022-01-31
FALSE | 188 | FOYER_ENTRY2 | Foyer/Entry | Bifold mirrored door set - High grade - Double | 0 | Average | 1 | 899.75 | EA | 0 | 899.75 | Dwelling | 0 | 1079.71 | 100 | Percent | 0 | Yes | 1079.71 | Yes | No | DOR | BFMIR+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 189 | FOYER_ENTRY2 | Foyer/Entry | Door opening (jamb & casing) - 36"to60"wide - paint grade | 0 | Average | 1 | 244.82 | EA | 0 | 244.82 | Dwelling | 0 | 293.78 | 150 | Percent | 0 | Yes | 293.78 | Yes | No | FNC | DOP> | DAVID.SO |  | 2022-01-22
FALSE | 190 | FOYER_ENTRY2 | Foyer/Entry | Paint door or window opening - Large - 2 coats (per side) | 0 | Average | 1 | 62.64 | EA | 0 | 62.64 | Dwelling | 0 | 75.16 | 15 | Percent | 0 | Yes | 75.16 | Yes | No | PNT | OP> | DAVID.SO |  | 2022-01-22
FALSE | 191 | FOYER_ENTRY2 | Foyer/Entry | Crown moulding - 4 1/4" stain grade | 0 | Average | 31.25 | 273.75 | LF | 0 | 8.76 | Dwelling | 0 | 328.51 | 150 | Percent | 0 | Yes | 328.51 | Yes | No | FNC | CWN>+ | DAVID.SO |  | 2022-01-31
FALSE | 192 | FOYER_ENTRY2 | Foyer/Entry | Stain & finish crown moulding | 0 | Average | 31.25 | 88.75 | LF | 0 | 2.84 | Dwelling | 0 | 106.51 | 15 | Percent | 0 | Yes | 106.51 | Yes | No | PNT | CWNS | DAVID.SO |  | 2022-01-31
FALSE | 193 | FOYER_ENTRY2 | Foyer/Entry | Mask and prep for paint - plastic, paper, tape (per LF) | 0 | Average | 62.5 | 140.63 | LF | 0 | 2.25 | Dwelling | 0 | 168.75 | 15 | Percent | 0 | Yes | 168.75 | Yes | No | PNT | MASKLF | DAVID.SO |  | 2022-01-31
FALSE | 194 | FOYER_ENTRY2 | Foyer/Entry | Closet Organizer - Melamine - Premium grade | 0 | Average | 5 | 978.7 | LF | 0 | 195.74 | Dwelling | 0 | 1174.44 | 150 | Percent | 0 | Yes | 1174.44 | Yes | No | FNC | CLOSM++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 195 | FOYER_ENTRY2 | Foyer/Entry | Paint door or window opening - Large - 2 coats (per side) | 0 | Average | 3 | 187.92 | EA | 0 | 62.64 | Dwelling | 0 | 225.5 | 15 | Percent | 0 | Yes | 225.5 | Yes | No | PNT | OP> | DAVID.SO |  | 2022-01-22
FALSE | 196 | BATHROOM2 | Bathroom | 110 volt copper wiring run, box and outlet | 0 | Average | 3.46 | 305.31 | EA | 0 | 88.24 | Dwelling | 0 | 366.37 | 100 | Percent | 0 | Yes | 366.37 | Yes | No | ELE | 110 | DAVID.SO |  | 2022-01-27
FALSE | 197 | BATHROOM2 | Bathroom | 110 volt copper wiring run, box and switch | 0 | Average | 2 | 177.68 | EA | 0 | 88.84 | Dwelling | 0 | 213.22 | 100 | Percent | 0 | Yes | 213.22 | Yes | No | ELE | 110S | DAVID.SO |  | 2022-01-27
FALSE | 198 | BATHROOM2 | Bathroom | Batt insulation - 6" - R20 - unfaced batt | 0 | Average | 40 | 72.4 | SF | 0 | 1.81 | Dwelling | 0 | 86.88 | 150 | Percent | 0 | Yes | 86.88 | Yes | No | INS | BT6 | DAVID.SO |  | 2022-01-22
FALSE | 199 | BATHROOM2 | Bathroom | Polyethylene vapor barrier, seam taping & joint caulking | 0 | Average | 84.17 | 52.19 | SF | 0 | 0.62 | Dwelling | 0 | 62.63 | 150 | Percent | 0 | Yes | 62.63 | Yes | No | INS | VISTC | DAVID.SO |  | 2022-01-22
FALSE | 200 | BATHROOM2 | Bathroom | 1/2" drywall - hung, taped, floated, ready for paint | 0 | Average | 265.5 | 894.74 | SF | 0 | 3.37 | Dwelling | 0 | 1073.68 | 150 | Percent | 0 | Yes | 1073.68 | Yes | No | DRY | 1/2 | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 201 | BATHROOM2 | Bathroom | Mask wall - plastic, paper, tape (per LF) | 0 | Average | 27.67 | 48.7 | LF | 0 | 1.76 | Dwelling | 0 | 58.44 | 150 | Percent | 0 | Yes | 58.44 | Yes | No | DRY | MASKLF | DAVID.SO |  | 2022-01-31
FALSE | 202 | BATHROOM2 | Bathroom | Texture drywall - smooth / skim coat | 0 | Average | 88.33 | 175.78 | SF | 0 | 1.99 | Dwelling | 0 | 210.94 | 150 | Percent | 0 | Yes | 210.94 | Yes | No | DRY | TEX++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 203 | BATHROOM2 | Bathroom | Seal/prime then paint the ceiling twice (3 coats) - 2 colours | 0 | Average | 44.17 | 118.38 | SF | 0 | 2.68 | Dwelling | 0 | 142.06 | 15 | Percent | 0 | Yes | 142.06 | Yes | No | PNT | SP2+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 204 | BATHROOM2 | Bathroom | Vanity - Premium grade | 0 | Average | 3 | 1428.78 | LF | 0 | 476.26 | Dwelling | 0 | 1714.54 | 50 | Percent | 0 | Yes | 1714.54 | Yes | No | CAB | VAN++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 205 | BATHROOM2 | Bathroom | Countertop - solid surface | 0 | Average | 3 | 243.06 | SF | 0 | 81.02 | Dwelling | 0 | 291.68 | 25 | Percent | 0 | Yes | 291.68 | Yes | No | CAB | CTSS | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 206 | BATHROOM2 | Bathroom | Sink faucet - Bathroom - Deluxe grade | 0 | Average | 1 | 622.97 | EA | 0 | 622.97 | Dwelling | 0 | 747.57 | 20 | Percent | 0 | Yes | 747.57 | Yes | No | PLM | FAUBAD | DAVID.SO |  | 2022-02-01
FALSE | 207 | BATHROOM2 | Bathroom | Sink - single - High grade | 0 | Average | 1 | 444.71 | EA | 0 | 444.71 | Dwelling | 0 | 533.65 | 50 | Percent | 0 | Yes | 533.65 | Yes | No | PLM | SNK+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 208 | BATHROOM2 | Bathroom | Toilet - High grade | 0 | Average | 1 | 776.6 | EA | 0 | 776.6 | Dwelling | 0 | 931.92 | 150 | Percent | 0 | Yes | 931.92 | Yes | No | PLM | TLT+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 209 | BATHROOM2 | Bathroom | Fibreglass tub & shower combination - Premium grade | 0 | Average | 1 | 1657.51 | EA | 0 | 1657.51 | Dwelling | 0 | 1989.01 | 50 | Percent | 0 | Yes | 1989.01 | Yes | No | PLM | TUB/S++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 210 | BATHROOM2 | Bathroom | Tub/shower faucet - Premium grade | 0 | Average | 1 | 539.82 | EA | 0 | 539.82 | Dwelling | 0 | 647.78 | 20 | Percent | 0 | Yes | 647.78 | Yes | No | PLM | TSFAU++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 211 | BATHROOM2 | Bathroom | Vinyl - metal transition strip | 0 | Average | 3 | 14.1 | LF | 0 | 4.7 | Dwelling | 0 | 16.92 | 50 | Percent | 0 | Yes | 16.92 | Yes | No | FCV | EDGE | DAVID.SO |  | 2022-01-22
FALSE | 212 | BATHROOM2 | Bathroom | Underlayment - sound/crack membrane - up to 40 mil | 0 | Average | 44.17 | 122.79 | SF | 0 | 2.78 | Dwelling | 0 | 147.35 | 15 | Percent | 0 | Yes | 147.35 | Yes | No | FCT | US | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 213 | BATHROOM2 | Bathroom | Tile floor covering - Premium grade | 0 | Average | 44.17 | 926.69 | SF | 0 | 20.98 | Dwelling | 0 | 1112.03 | 100 | Percent | 0 | Yes | 1112.03 | Yes | No | FCT | AV++ | DAVID.SO |  | 2022-01-31
FALSE | 214 | BATHROOM2 | Bathroom | Baseboard - 5 1/4" hardwood | 0 | Average | 27.67 | 258.71 | LF | 0 | 9.35 | Dwelling | 0 | 310.45 | 150 | Percent | 0 | Yes | 310.45 | Yes | No | FNC | B5H | DAVID.SO |  | 2022-01-31
FALSE | 215 | BATHROOM2 | Bathroom | Finish baseboard - oversized - 1 coat urethane | 0 | Average | 27.67 | 52.3 | LF | 0 | 1.89 | Dwelling | 0 | 62.76 | 15 | Percent | 0 | Yes | 62.76 | Yes | No | PNT | BS>1 | DAVID.SO |  | 2022-01-31
FALSE | 216 | BATHROOM2 | Bathroom | Light fixture - wall sconce - large - High grade | 0 | Average | 1 | 288.76 | EA | 0 | 288.76 | Dwelling | 0 | 346.52 | 20 | Percent | 0 | Yes | 346.52 | Yes | No | LIT | SCON>+ | DAVID.SO |  | 2022-02-07
FALSE | 217 | BEDROOM_2 | Bedroom 1 | 110 volt copper wiring run, box and outlet | 0 | Average | 7.08 | 624.74 | EA | 0 | 88.24 | Dwelling | 0 | 749.68 | 100 | Percent | 0 | Yes | 749.68 | Yes | No | ELE | 110 | DAVID.SO |  | 2022-01-27
FALSE | 218 | BEDROOM_2 | Bedroom 1 | 110 volt copper wiring run, box and switch | 0 | Average | 1 | 88.84 | EA | 0 | 88.84 | Dwelling | 0 | 106.6 | 100 | Percent | 0 | Yes | 106.6 | Yes | No | ELE | 110S | DAVID.SO |  | 2022-01-27
FALSE | 219 | BEDROOM_2 | Bedroom 1 | Batt insulation - 6" - R20 - unfaced batt | 0 | Average | 192 | 347.52 | SF | 0 | 1.81 | Dwelling | 0 | 417.02 | 150 | Percent | 0 | Yes | 417.02 | Yes | No | INS | BT6 | DAVID.SO |  | 2022-01-22
FALSE | 220 | BEDROOM_2 | Bedroom 1 | Polyethylene vapor barrier, seam taping & joint caulking | 0 | Average | 556.13 | 344.8 | SF | 0 | 0.62 | Dwelling | 0 | 413.76 | 150 | Percent | 0 | Yes | 413.76 | Yes | No | INS | VISTC | DAVID.SO |  | 2022-01-22
FALSE | 221 | BEDROOM_2 | Bedroom 1 | 1/2" drywall - hung, taped, floated, ready for paint | 0 | Average | 556.13 | 1874.16 | SF | 0 | 3.37 | Dwelling | 0 | 2249 | 150 | Percent | 0 | Yes | 2249 | Yes | No | DRY | 1/2 | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 222 | BEDROOM_2 | Bedroom 1 | Seal the walls and ceiling w/latex based stain blocker - one coat | 0 | Average | 556.13 | 595.06 | SF | 0 | 1.07 | Dwelling | 0 | 714.08 | 15 | Percent | 0 | Yes | 714.08 | Yes | No | PNT | S | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 223 | BEDROOM_2 | Bedroom 1 | Mask wall - plastic, paper, tape (per LF) | 0 | Average | 56.67 | 99.74 | LF | 0 | 1.76 | Dwelling | 0 | 119.68 | 150 | Percent | 0 | Yes | 119.68 | Yes | No | DRY | MASKLF | DAVID.SO |  | 2022-01-27
FALSE | 224 | BEDROOM_2 | Bedroom 1 | Texture drywall - smooth / skim coat | 0 | Average | 205.58 | 409.1 | SF | 0 | 1.99 | Dwelling | 0 | 490.92 | 150 | Percent | 0 | Yes | 490.92 | Yes | No | DRY | TEX++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 225 | BEDROOM_2 | Bedroom 1 | Light fixture - Premium grade | 0 | Average | 1 | 194 | EA | 0 | 194 | Dwelling | 0 | 232.8 | 20 | Percent | 0 | Yes | 232.8 | Yes | No | LIT | AV++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 226 | BEDROOM_2 | Bedroom 1 | Paint the walls and ceiling - two coats - 2 colours | 0 | Average | 556.13 | 1140.07 | SF | 0 | 2.05 | Dwelling | 0 | 1368.09 | 15 | Percent | 0 | Yes | 1368.09 | Yes | No | PNT | P2+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 227 | BEDROOM_2 | Bedroom 1 | Pre-finished solid wood flooring - Premium grade | 0 | Average | 102.79 | 1870.78 | SF | 0 | 18.2 | Dwelling | 0 | 2244.94 | 150 | Percent | 0 | Yes | 2244.94 | Yes | No | FCW | AVPF++ | DAVID.SO |  | 2022-01-31
FALSE | 228 | BEDROOM_2 | Bedroom 1 | Baseboard - 5 1/4" hardwood | 0 | Average | 56.67 | 529.86 | LF | 0 | 9.35 | Dwelling | 0 | 635.84 | 150 | Percent | 0 | Yes | 635.84 | Yes | No | FNC | B5H | DAVID.SO |  | 2022-01-31
FALSE | 229 | BEDROOM_2 | Bedroom 1 | Finish baseboard - oversized - 1 coat urethane | 0 | Average | 56.67 | 107.11 | LF | 0 | 1.89 | Dwelling | 0 | 128.53 | 15 | Percent | 0 | Yes | 128.53 | Yes | No | PNT | BS>1 | DAVID.SO |  | 2022-01-31
FALSE | 230 | BEDROOM_2 | Bedroom 1 | Bifold mirrored door set - High grade - Double | 0 | Average | 1 | 899.75 | EA | 0 | 899.75 | Dwelling | 0 | 1079.71 | 100 | Percent | 0 | Yes | 1079.71 | Yes | No | DOR | BFMIR+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 231 | BEDROOM_2 | Bedroom 1 | Door opening (jamb & casing) - 36"to60"wide - paint grade | 0 | Average | 1 | 244.82 | EA | 0 | 244.82 | Dwelling | 0 | 293.78 | 150 | Percent | 0 | Yes | 293.78 | Yes | No | FNC | DOP> | DAVID.SO |  | 2022-01-22
FALSE | 232 | BEDROOM_2 | Bedroom 1 | Paint door or window opening - Large - 2 coats (per side) | 0 | Average | 1 | 62.64 | EA | 0 | 62.64 | Dwelling | 0 | 75.16 | 15 | Percent | 0 | Yes | 75.16 | Yes | No | PNT | OP> | DAVID.SO |  | 2022-01-22
FALSE | 233 | BEDROOM_2 | Bedroom 1 | Crown moulding - 4 1/4" stain grade | 0 | Average | 56.67 | 496.43 | LF | 0 | 8.76 | Dwelling | 0 | 595.71 | 150 | Percent | 0 | Yes | 595.71 | Yes | No | FNC | CWN>+ | DAVID.SO |  | 2022-01-31
FALSE | 234 | BEDROOM_2 | Bedroom 1 | Stain & finish crown moulding | 0 | Average | 56.67 | 160.94 | LF | 0 | 2.84 | Dwelling | 0 | 193.12 | 15 | Percent | 0 | Yes | 193.12 | Yes | No | PNT | CWNS | DAVID.SO |  | 2022-01-31
FALSE | 235 | BEDROOM_2 | Bedroom 1 | Mask and prep for paint - plastic, paper, tape (per LF) | 0 | Average | 113.33 | 254.99 | LF | 0 | 2.25 | Dwelling | 0 | 305.99 | 15 | Percent | 0 | Yes | 305.99 | Yes | No | PNT | MASKLF | DAVID.SO |  | 2022-01-31
FALSE | 236 | BEDROOM_2 | Bedroom 1 | Closet Organizer - Melamine - Premium grade | 0 | Average | 5 | 978.7 | LF | 0 | 195.74 | Dwelling | 0 | 1174.44 | 150 | Percent | 0 | Yes | 1174.44 | Yes | No | FNC | CLOSM++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 237 | OFFICE2 | Office | 110 volt copper wiring run, box and outlet | 0 | Average | 4.4 | 388.26 | EA | 0 | 88.24 | Dwelling | 0 | 465.92 | 100 | Percent | 0 | Yes | 465.92 | Yes | No | ELE | 110 | DAVID.SO |  | 2022-01-27
FALSE | 238 | OFFICE2 | Office | 110 volt copper wiring run, box and switch | 0 | Average | 1 | 88.84 | EA | 0 | 88.84 | Dwelling | 0 | 106.6 | 100 | Percent | 0 | Yes | 106.6 | Yes | No | ELE | 110S | DAVID.SO |  | 2022-01-27
FALSE | 239 | OFFICE2 | Office | Batt insulation - 6" - R20 - unfaced batt | 0 | Average | 72 | 130.32 | SF | 0 | 1.81 | Dwelling | 0 | 156.38 | 150 | Percent | 0 | Yes | 156.38 | Yes | No | INS | BT6 | DAVID.SO |  | 2022-01-22
FALSE | 240 | OFFICE2 | Office | Polyethylene vapor barrier, seam taping & joint caulking | 0 | Average | 358.63 | 222.35 | SF | 0 | 0.62 | Dwelling | 0 | 266.83 | 150 | Percent | 0 | Yes | 266.83 | Yes | No | INS | VISTC | DAVID.SO |  | 2022-01-22
FALSE | 241 | OFFICE2 | Office | 1/2" drywall - hung, taped, floated, ready for paint | 0 | Average | 358.63 | 1208.58 | SF | 0 | 3.37 | Dwelling | 0 | 1450.3 | 150 | Percent | 0 | Yes | 1450.3 | Yes | No | DRY | 1/2 | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 242 | OFFICE2 | Office | Seal the walls w/latex based stain blocker - one coat | 0 | Average | 281.33 | 301.02 | SF | 0 | 1.07 | Dwelling | 0 | 361.22 | 15 | Percent | 0 | Yes | 361.22 | Yes | No | PNT | S | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 243 | OFFICE2 | Office | Mask wall - plastic, paper, tape (per LF) | 0 | Average | 35.17 | 61.9 | LF | 0 | 1.76 | Dwelling | 0 | 74.28 | 150 | Percent | 0 | Yes | 74.28 | Yes | No | DRY | MASKLF | DAVID.SO |  | 2022-01-27
FALSE | 244 | OFFICE2 | Office | Texture drywall - smooth / skim coat | 0 | Average | 154.58 | 307.61 | SF | 0 | 1.99 | Dwelling | 0 | 369.13 | 150 | Percent | 0 | Yes | 369.13 | Yes | No | DRY | TEX++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 245 | OFFICE2 | Office | Light fixture - Premium grade | 0 | Average | 1 | 194 | EA | 0 | 194 | Dwelling | 0 | 232.8 | 20 | Percent | 0 | Yes | 232.8 | Yes | No | LIT | AV++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 246 | OFFICE2 | Office | Paint the walls and ceiling - two coats - 2 colours | 0 | Average | 358.63 | 735.19 | SF | 0 | 2.05 | Dwelling | 0 | 882.23 | 15 | Percent | 0 | Yes | 882.23 | Yes | No | PNT | P2+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 247 | OFFICE2 | Office | Pre-finished solid wood flooring - Premium grade | 0 | Average | 77.29 | 1406.68 | SF | 0 | 18.2 | Dwelling | 0 | 1688.02 | 150 | Percent | 0 | Yes | 1688.02 | Yes | No | FCW | AVPF++ | DAVID.SO |  | 2022-01-31
FALSE | 248 | OFFICE2 | Office | Baseboard - 5 1/4" hardwood | 0 | Average | 35.17 | 328.84 | LF | 0 | 9.35 | Dwelling | 0 | 394.6 | 150 | Percent | 0 | Yes | 394.6 | Yes | No | FNC | B5H | DAVID.SO |  | 2022-01-31
FALSE | 249 | OFFICE2 | Office | Finish baseboard - oversized - 1 coat urethane | 0 | Average | 35.17 | 66.47 | LF | 0 | 1.89 | Dwelling | 0 | 79.77 | 15 | Percent | 0 | Yes | 79.77 | Yes | No | PNT | BS>1 | DAVID.SO |  | 2022-01-31
FALSE | 250 | OFFICE2 | Office | Crown moulding - 4 1/4" stain grade | 0 | Average | 35.17 | 308.09 | LF | 0 | 8.76 | Dwelling | 0 | 369.71 | 150 | Percent | 0 | Yes | 369.71 | Yes | No | FNC | CWN>+ | DAVID.SO |  | 2022-01-31
FALSE | 251 | OFFICE2 | Office | Stain & finish crown moulding | 0 | Average | 35.17 | 99.88 | LF | 0 | 2.84 | Dwelling | 0 | 119.86 | 15 | Percent | 0 | Yes | 119.86 | Yes | No | PNT | CWNS | DAVID.SO |  | 2022-01-31
FALSE | 252 | OFFICE2 | Office | Mask and prep for paint - plastic, paper, tape (per LF) | 0 | Average | 70.33 | 158.24 | LF | 0 | 2.25 | Dwelling | 0 | 189.88 | 15 | Percent | 0 | Yes | 189.88 | Yes | No | PNT | MASKLF | DAVID.SO |  | 2022-01-31
FALSE | 253 | GARAGE | Garage | 110 volt copper wiring run, box and outlet | 0 | Average | 10.5 | 926.52 | EA | 0 | 88.24 | Dwelling | 0 | 1111.82 | 100 | Percent | 0 | Yes | 1111.82 | Yes | No | ELE | 110 | DAVID.SO |  | 2022-01-27
FALSE | 254 | GARAGE | Garage | 110 volt copper wiring run, box and switch | 0 | Average | 2 | 177.68 | EA | 0 | 88.84 | Dwelling | 0 | 213.22 | 100 | Percent | 0 | Yes | 213.22 | Yes | No | ELE | 110S | DAVID.SO |  | 2022-01-27
FALSE | 255 | GARAGE | Garage | Batt insulation - 6" - R20 - unfaced batt | 0 | Average | 672 | 1216.32 | SF | 0 | 1.81 | Dwelling | 0 | 1459.58 | 150 | Percent | 0 | Yes | 1459.58 | Yes | No | INS | BT6 | DAVID.SO |  | 2022-01-22
FALSE | 256 | GARAGE | Garage | Blown-in insulation - 16" depth - R44 | 0 | Average | 440 | 1122 | SF | 0 | 2.55 | Dwelling | 0 | 1346.4 | 150 | Percent | 0 | Yes | 1346.4 | Yes | No | INS | BI16 | DAVID.SO |  | 2022-01-27
FALSE | 257 | GARAGE | Garage | Polyethylene vapor barrier, seam taping & joint caulking | 0 | Average | 1112 | 689.44 | SF | 0 | 0.62 | Dwelling | 0 | 827.32 | 150 | Percent | 0 | Yes | 827.32 | Yes | No | INS | VISTC | DAVID.SO |  | 2022-01-22
FALSE | 258 | GARAGE | Garage | 1/2" drywall - hung, taped, floated, ready for paint | 0 | Average | 1112 | 3747.44 | SF | 0 | 3.37 | Dwelling | 0 | 4496.92 | 150 | Percent | 0 | Yes | 4496.92 | Yes | No | DRY | 1/2 | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 259 | GARAGE | Garage | Seal/prime then paint the walls twice (3 coats) | 0 | Average | 672 | 1478.4 | SF | 0 | 2.2 | Dwelling | 0 | 1774.08 | 15 | Percent | 0 | Yes | 1774.08 | Yes | No | PNT | SP2 | DAVID.SO |  | 2022-01-22
FALSE | 260 | GARAGE | Garage | Light fixture - High grade | 0 | Average | 2 | 219 | EA | 0 | 109.5 | Dwelling | 0 | 262.8 | 20 | Percent | 0 | Yes | 262.8 | Yes | No | LIT | AV+ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 261 | GARAGE | Garage | Exterior light fixture - Premium grade | 0 | Average | 4 | 685.04 | EA | 0 | 171.26 | Dwelling | 0 | 822.04 | 20 | Percent | 0 | Yes | 822.04 | Yes | No | LIT | X++ | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 262 | GARAGE | Garage | Overhead door & hardware - 16' x 8' - Premium grade | 0 | Average | 1 | 3259.14 | EA | 0 | 3259.14 | Dwelling | 0 | 3910.96 | 35 | Percent | 0 | Yes | 3910.96 | Yes | No | DOR | OH16++> | DAVID.SO |  | 2022-01-31 | Price List Item
FALSE | 263 | GARAGE | Garage | Epoxy finish - two coats over concrete floor - non-slip | 0 | Average | 440 | 2873.2 | SF | 0 | 6.53 | Dwelling | 0 | 3447.84 | 15 | Percent | 0 | Yes | 3447.84 | Yes | No | PNT | EPX2N | DAVID.SO |  | 2022-01-31

## response
Excluded | # | Group Code | Group Description | Desc | Age | Condition | Qty | Item Amount | Unit | Reported Cost | Unit Cost | Coverage | Sales Tax | RCV | Life | Depreciation Type | Depreciation Amount | Recoverable | ACV | Tax | Replace | Cat | Sel | Owner | Original Vendor | Date | Source Name
FALSE | 1 | MAIN_LEVEL | Main Level | Equipment setup, take down, and monitoring (hourly charge) | 0 | Average | 10 | 725.6 | HR | 0 | 72.56 | Dwelling | 0 | 870.72 | 0 | Percent | 0 | Yes | 870.72 | Yes | No | WTR | EQ | DAVID.SO |  | 2022-01-14
FALSE | 2 | MAIN_LEVEL | Main Level | Dumpster load - Approx. 40 yards, 7-8 tons of debris | 0 | Average | 4 | 5932 | EA | 0 | 1483 | Dwelling | 0 | 7118.4 | 0 | Percent | 0 | Yes | 7118.4 | Yes | No | DMO | DUMP>> | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 3 | DINING_ROOM2 | Dining Room | Demolish/remove - bedroom/room (up to 200 sf) | 0 | Average | 121.67 | 829.79 | SF | 0 | 6.82 | Dwelling | 0 | 995.75 | 0 | Percent | 0 | Yes | 995.75 | Yes | No | DMO | HRBDR | DAVID.SO |  | 2022-01-27
FALSE | 4 | DINING_ROOM2 | Dining Room | Clean with pressure/chemical spray | 0 | Average | 121.67 | 53.53 | SF | 0 | 0.44 | Dwelling | 0 | 64.23 | 0 | Percent | 0 | Yes | 64.23 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 5 | DINING_ROOM2 | Dining Room | Apply plant-based anti-microbial agent to the floor | 0 | Average | 121.67 | 42.58 | SF | 0 | 0.35 | Dwelling | 0 | 51.1 | 0 | Percent | 0 | Yes | 51.1 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 6 | DINING_ROOM2 | Dining Room | Air mover (per 24 hour period) - No monitoring | 0 | Average | 6 | 201 | EA | 0 | 33.5 | Dwelling | 0 | 241.2 | 0 | Percent | 0 | Yes | 241.2 | Yes | No | WTR | DRY | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 7 | KITCHEN2 | Kitchen | Demolish/remove - kitchen/laundry | 0 | Average | 111 | 1581.75 | SF | 0 | 14.25 | Dwelling | 0 | 1898.11 | 0 | Percent | 0 | Yes | 1898.11 | Yes | No | DMO | HRK | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 8 | KITCHEN2 | Kitchen | Clean with pressure/chemical spray | 0 | Average | 111 | 48.84 | SF | 0 | 0.44 | Dwelling | 0 | 58.6 | 0 | Percent | 0 | Yes | 58.6 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 9 | KITCHEN2 | Kitchen | Apply plant-based anti-microbial agent to the floor | 0 | Average | 111 | 38.85 | SF | 0 | 0.35 | Dwelling | 0 | 46.63 | 0 | Percent | 0 | Yes | 46.63 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 10 | KITCHEN2 | Kitchen | Dehumidifier (per 24 hour period) - Large - No monitoring | 0 | Average | 3 | 225 | EA | 0 | 75 | Dwelling | 0 | 270 | 0 | Percent | 0 | Yes | 270 | Yes | No | WTR | DHM> | DAVID.SO |  | 2022-01-27
FALSE | 11 | KITCHEN2 | Kitchen | Air mover (per 24 hour period) - No monitoring | 0 | Average | 6 | 201 | EA | 0 | 33.5 | Dwelling | 0 | 241.2 | 0 | Percent | 0 | Yes | 241.2 | Yes | No | WTR | DRY | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 12 | LIVING_ROOM2 | Living Room | Demolish/remove - bedroom/room (up to 200 sf) | 0 | Average | 162.67 | 1109.41 | SF | 0 | 6.82 | Dwelling | 0 | 1331.29 | 0 | Percent | 0 | Yes | 1331.29 | Yes | No | DMO | HRBDR | DAVID.SO |  | 2022-01-27
FALSE | 13 | LIVING_ROOM2 | Living Room | Clean with pressure/chemical spray | 0 | Average | 162.67 | 71.57 | SF | 0 | 0.44 | Dwelling | 0 | 85.89 | 0 | Percent | 0 | Yes | 85.89 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 14 | LIVING_ROOM2 | Living Room | Apply plant-based anti-microbial agent to the floor | 0 | Average | 162.67 | 56.93 | SF | 0 | 0.35 | Dwelling | 0 | 68.31 | 0 | Percent | 0 | Yes | 68.31 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 15 | LIVING_ROOM2 | Living Room | Air mover (per 24 hour period) - No monitoring | 0 | Average | 6 | 201 | EA | 0 | 33.5 | Dwelling | 0 | 241.2 | 0 | Percent | 0 | Yes | 241.2 | Yes | No | WTR | DRY | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 16 | HALLWAY | Hallway | Demolish/remove - bedroom/room (up to 200 sf) | 0 | Average | 110.5 | 753.61 | SF | 0 | 6.82 | Dwelling | 0 | 904.33 | 0 | Percent | 0 | Yes | 904.33 | Yes | No | DMO | HRBDR | DAVID.SO |  | 2022-01-27
FALSE | 17 | HALLWAY | Hallway | Clean with pressure/chemical spray | 0 | Average | 110.5 | 48.62 | SF | 0 | 0.44 | Dwelling | 0 | 58.34 | 0 | Percent | 0 | Yes | 58.34 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 18 | HALLWAY | Hallway | Apply plant-based anti-microbial agent to the floor | 0 | Average | 110.5 | 38.68 | SF | 0 | 0.35 | Dwelling | 0 | 46.42 | 0 | Percent | 0 | Yes | 46.42 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 19 | BEDROOM_2 | Bedroom 2 | Demolish/remove - bedroom/room (up to 200 sf) | 0 | Average | 117.22 | 799.44 | SF | 0 | 6.82 | Dwelling | 0 | 959.32 | 0 | Percent | 0 | Yes | 959.32 | Yes | No | DMO | HRBDR | DAVID.SO |  | 2022-01-27
FALSE | 20 | BEDROOM_2 | Bedroom 2 | Clean with pressure/chemical spray | 0 | Average | 117.22 | 51.58 | SF | 0 | 0.44 | Dwelling | 0 | 61.9 | 0 | Percent | 0 | Yes | 61.9 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 21 | BEDROOM_2 | Bedroom 2 | Apply plant-based anti-microbial agent to the floor | 0 | Average | 117.22 | 41.03 | SF | 0 | 0.35 | Dwelling | 0 | 49.23 | 0 | Percent | 0 | Yes | 49.23 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 22 | BEDROOM_2 | Bedroom 2 | Air mover (per 24 hour period) - No monitoring | 0 | Average | 3 | 100.5 | EA | 0 | 33.5 | Dwelling | 0 | 120.6 | 0 | Percent | 0 | Yes | 120.6 | Yes | No | WTR | DRY | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 23 | MASTER_BEDRO | Master Bedroom | Demolish/remove - bedroom/room (up to 200 sf) | 0 | Average | 157.5 | 1074.15 | SF | 0 | 6.82 | Dwelling | 0 | 1288.99 | 0 | Percent | 0 | Yes | 1288.99 | Yes | No | DMO | HRBDR | DAVID.SO |  | 2022-01-27
FALSE | 24 | MASTER_BEDRO | Master Bedroom | Clean with pressure/chemical spray | 0 | Average | 157.5 | 69.3 | SF | 0 | 0.44 | Dwelling | 0 | 83.16 | 0 | Percent | 0 | Yes | 83.16 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 25 | MASTER_BEDRO | Master Bedroom | Apply plant-based anti-microbial agent to the floor | 0 | Average | 157.5 | 55.13 | SF | 0 | 0.35 | Dwelling | 0 | 66.15 | 0 | Percent | 0 | Yes | 66.15 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 26 | MASTER_BEDRO | Master Bedroom | Dehumidifier (per 24 hour period) - Large - No monitoring | 0 | Average | 3 | 225 | EA | 0 | 75 | Dwelling | 0 | 270 | 0 | Percent | 0 | Yes | 270 | Yes | No | WTR | DHM> | DAVID.SO |  | 2022-01-27
FALSE | 27 | MASTER_BEDRO | Master Bedroom | Air mover (per 24 hour period) - No monitoring | 0 | Average | 6 | 201 | EA | 0 | 33.5 | Dwelling | 0 | 241.2 | 0 | Percent | 0 | Yes | 241.2 | Yes | No | WTR | DRY | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 28 | FOYER_ENTRY | Foyer/Entry | Demolish/remove - bedroom/room (up to 200 sf) | 0 | Average | 51.96 | 354.37 | SF | 0 | 6.82 | Dwelling | 0 | 425.25 | 0 | Percent | 0 | Yes | 425.25 | Yes | No | DMO | HRBDR | DAVID.SO |  | 2022-01-27
FALSE | 29 | FOYER_ENTRY | Foyer/Entry | Clean with pressure/chemical spray | 0 | Average | 51.96 | 22.86 | SF | 0 | 0.44 | Dwelling | 0 | 27.44 | 0 | Percent | 0 | Yes | 27.44 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 30 | FOYER_ENTRY | Foyer/Entry | Apply plant-based anti-microbial agent to the floor | 0 | Average | 51.96 | 18.19 | SF | 0 | 0.35 | Dwelling | 0 | 21.83 | 0 | Percent | 0 | Yes | 21.83 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 31 | BATHROOM | Bathroom | Demolish/remove - bathroom (up to 50 sf) | 0 | Average | 44.17 | 852.48 | SF | 0 | 19.3 | Dwelling | 0 | 1022.98 | 0 | Percent | 0 | Yes | 1022.98 | Yes | No | DMO | HRBR | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 32 | BATHROOM | Bathroom | Clean with pressure/chemical spray | 0 | Average | 44.17 | 19.43 | SF | 0 | 0.44 | Dwelling | 0 | 23.31 | 0 | Percent | 0 | Yes | 23.31 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 33 | BATHROOM | Bathroom | Apply plant-based anti-microbial agent to the floor | 0 | Average | 44.17 | 15.46 | SF | 0 | 0.35 | Dwelling | 0 | 18.56 | 0 | Percent | 0 | Yes | 18.56 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 34 | BATHROOM | Bathroom | Dehumidifier (per 24 hour period) - Large - No monitoring | 0 | Average | 3 | 225 | EA | 0 | 75 | Dwelling | 0 | 270 | 0 | Percent | 0 | Yes | 270 | Yes | No | WTR | DHM> | DAVID.SO |  | 2022-01-27
FALSE | 35 | BEDROOM_1 | Bedroom 1 | Demolish/remove - bedroom/room (up to 200 sf) | 0 | Average | 102.79 | 701.03 | SF | 0 | 6.82 | Dwelling | 0 | 841.23 | 0 | Percent | 0 | Yes | 841.23 | Yes | No | DMO | HRBDR | DAVID.SO |  | 2022-01-27
FALSE | 36 | BEDROOM_1 | Bedroom 1 | Clean with pressure/chemical spray | 0 | Average | 102.79 | 45.23 | SF | 0 | 0.44 | Dwelling | 0 | 54.27 | 0 | Percent | 0 | Yes | 54.27 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 37 | BEDROOM_1 | Bedroom 1 | Apply plant-based anti-microbial agent to the floor | 0 | Average | 102.79 | 35.98 | SF | 0 | 0.35 | Dwelling | 0 | 43.18 | 0 | Percent | 0 | Yes | 43.18 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 38 | BEDROOM_1 | Bedroom 1 | Dehumidifier (per 24 hour period) - Large - No monitoring | 0 | Average | 3 | 225 | EA | 0 | 75 | Dwelling | 0 | 270 | 0 | Percent | 0 | Yes | 270 | Yes | No | WTR | DHM> | DAVID.SO |  | 2022-01-27
FALSE | 39 | BEDROOM_1 | Bedroom 1 | Air mover (per 24 hour period) - No monitoring | 0 | Average | 3 | 100.5 | EA | 0 | 33.5 | Dwelling | 0 | 120.6 | 0 | Percent | 0 | Yes | 120.6 | Yes | No | WTR | DRY | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 40 | OFFICE | Office | Demolish/remove - bedroom/room (up to 200 sf) | 0 | Average | 77.29 | 527.12 | SF | 0 | 6.82 | Dwelling | 0 | 632.54 | 0 | Percent | 0 | Yes | 632.54 | Yes | No | DMO | HRBDR | DAVID.SO |  | 2022-01-27
FALSE | 41 | OFFICE | Office | Clean with pressure/chemical spray | 0 | Average | 77.29 | 34.01 | SF | 0 | 0.44 | Dwelling | 0 | 40.81 | 0 | Percent | 0 | Yes | 40.81 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-27
FALSE | 42 | OFFICE | Office | Apply plant-based anti-microbial agent to the floor | 0 | Average | 77.29 | 27.05 | SF | 0 | 0.35 | Dwelling | 0 | 32.47 | 0 | Percent | 0 | Yes | 32.47 | Yes | No | WTR | GRMB | DAVID.SO |  | 2022-01-27
FALSE | 43 | OFFICE | Office | Air mover (per 24 hour period) - No monitoring | 0 | Average | 3 | 100.5 | EA | 0 | 33.5 | Dwelling | 0 | 120.6 | 0 | Percent | 0 | Yes | 120.6 | Yes | No | WTR | DRY | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 44 | GARAGE | Garage | Tear out wet drywall, cleanup, bag for disposal | 0 | Average | 1112 | 1445.6 | SF | 0 | 1.3 | Dwelling | 0 | 1734.72 | 0 | Percent | 0 | Yes | 1734.72 | Yes | No | WTR | DRYW | DAVID.SO |  | 2022-01-27 | Price List Item
FALSE | 45 | GARAGE | Garage | Clean with pressure/chemical spray | 0 | Average | 440 | 193.6 | SF | 0 | 0.44 | Dwelling | 0 | 232.32 | 0 | Percent | 0 | Yes | 232.32 | Yes | No | CLN | PWASH | DAVID.SO |  | 2022-01-22
FALSE | 46 | GARAGE | Garage | Tear out and bag wet insulation | 0 | Average | 1112 | 1056.4 | SF | 0 | 0.95 | Dwelling | 0 | 1267.68 | 0 | Percent | 0 | Yes | 1267.68 | Yes | No | WTR | INS | DAVID.SO |  | 2022-01-27
FALSE | 47 | GARAGE | Garage | Air mover (per 24 hour period) - No monitoring | 0 | Average | 15 | 502.5 | EA | 0 | 33.5 | Dwelling | 0 | 603 | 0 | Percent | 0 | Yes | 603 | Yes | No | WTR | DRY | DAVID.SO |  | 2022-01-22

## Sheet2
Row Labels | Sum of RCV
Bathroom | 1334.85
Bedroom 1 | 1329.28
Bedroom 2 | 1191.05
Dining Room | 1352.28
Foyer/Entry | 474.52
Garage | 3837.72
Hallway | 1009.09
Kitchen | 2514.54
Living Room | 1726.69
Main Level | 7989.12
Master Bedroom | 1949.5
Office | 826.42
Grand Total | 25535.06